LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boola Boola-2 | REPORT No. : | 1 | DFS: | 0 | DATE : | 1-06-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 15.00m | LAST DEPTH : | 15.00m rkb | 24 HR PROGRESS: | 0 m | PTD : | 1500 m |
| TOTAL FUEL : | 19,600 | FUEL USAGE : | 700 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Spudded this well at 00:30hrs then Drilled 311mm hole from 15.00m to 79.00m |
| Next 24 Hrs Op | Drill ahead – Take surveys every 50m |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 Re-Run |  |  | Drilling |  |  | Density | 1.032 | S.G. |
| Size (mm) | 311 |  |  | Tripping |  |  | Viscosity | 43 | Sec |
| Make | Reed |  |  | Surveys |  |  | Water Loss |  | Cc |
| Type | EPH 41 |  |  | Rigged up | 24.00 |  | pH | 9.0 | Strip |
| IADC Code | 4-1-7 |  |  | Testing/tools |  |  | Filter Cake |  | 32 nd |
| Serial Number | NR 2008 |  |  | Circulate Sample |  |  | PV / YP |  | Cp/lb/100’ |
| Nozzles (32) | 18-18-18 |  |  | Casing |  |  | Gels |  | S/m |
| Depth in (m) | 15.00 |  |  | Cementing |  |  | Sand |  | % Vol |
| Depth out (m) |  |  |  | Surveys |  |  | Solids | 1.8 | % Vol |
| Total Metres |  |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service |  |  | K+ |  | Mg/l |
| WOB (kg) |  |  |  | Pick up BHA |  |  | Chlorides | 1,500 | Mg/l |
| RPM |  |  |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition |  |  |  | Repair rig |  |  | KCL | % |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 1,030 |
| Jet Velocity |  |  |  | Test BOPs |  |  | Cum Cost $ | 1,030 |
| B.H.A.: | 311mm –Near Bit Stab- Crossover sub |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 01:30 | Installed flo line and fill up line |  |  | ° at |  | m |  | Aus-Gel | 84 |
| 01:30 | 02:00 | Installed support beams on sub base |  |  | ° at |  | m |  | Dextrid |  |
| 02:00 | 02;30 | Installed man rider winch |  |  | ° at |  | m |  | Pac - R |  |
| 02:30 | 03:30 | Fixed Kelly spinner |  |  | ° at |  | m |  | Barite |  |
| 03:30 | 10:00 | Positioned rig and block to hang centre over well |  |  | ° at |  | m |  | Bulk Barite |  |
| 10:00 | 12:00 | Mixed spud mud |  |  | ° at |  | m |  | PHPA/ KCL |  |
| 12:00 | 19:00 | Drilled and installed Kelly and Mousehole socks |  |  | ° at |  | m |  | Caustic Soda | 1 |
| 19:00 | 21:30 | Re aligned rotary drive picked up handling tools |  |  |  |  |
| 21:30 | 23:30 | Made up 311mm Bit with Near Bit Stabilizer |  | PUMP 1 |  | PUMP 2 |
| 23:30 | 24;00 | Held pre spud meeting on Rig floor with rig site hands |  | Liner | 108 | mm |  | Liner | 108 | mm |
|  |  |  |  | Pressure |  | kPa |  | Pressure |  | KPa |
|  |  | Conducted rig inspection |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  | Function tested Emergency shut down systems |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM |  |
|  |  | 4 loads of water used today |  | LPM |  |  | LPM |  |
|  |  | 37 jnts of 244mm Casing arrived |  |  |  |  |
|  |  | 13 jnts from previous well on site Total 50 jnts |  | CEMENT DATA |  | LAST CASING |
|  |  | Halliburton units positioned on site |  | Sacks Halliburton |  |  | Size | 340 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 79.45 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | Conductor pipe |  |
|  |  |  |  | % |  |  |  | Joints | 1 |  |
|  |  |  |  | % |  |  |  | Length | 9.80 | m |
| Days since | LTA | 370 |  | Av. Wt |  |  | Depth | 15.00 m from RKB | m |

,66