LAKES OIL N.L.

DAILY DRILLING REPORT

| WELL: Boundary Creek-2 | REPORT No.: 29 | DATE: 07-11-05 |
| --- | --- | --- |
| DFS: 28 | 2400 DEPTH: 1963 | Last Depth: 1898 |
| 24hr Progress: 65 | PTD: 2500 | Total Fuel: |
| Fuel Usage: | Daily Cost: 50,154 | Cum Cost: 1,546,720 |
| 0600hrs Operation: Trip out for bit change -slow drill rate plus torque while drilling at 1974m |
| Next 24hr Operation: Trip out -change bits-drill ahead |
| Site Personnel: Lakes 3-AMC 1-Higgins 2-Hunt 18-Halliburton 1 |

| HOURLY OPERATIONS SUMMARY (000-2400hrs) | OPERATIONS BREAKDOWN |
| --- | --- |
| FROM | TO | OPERATION |  |  |
| 00:00 | 00:30 | Drilled cement to 121m | Drilling | 13.50 |
| 00:30 | 01:00 | Ran pipe to 177m | Tripping | 4.50 |
| 01:00 | 04:00 | Drilled cement from 177m to 200m | Surveys |  |
| 04:00 | 05:00 | Tested 9.625inch annulus to 7000kpa | Reaming |  |
| 05:00 | 06:00 | Drilled out cement plug 200m to 218m | Slip & Cut Block Line |  |
| 06:00 | 08:30 | Tripped in hole to 1099m | Circulate & Clean Hole | 0.50 |
| 08:30 | 09:00 | Filled pipe with mud | Cement Casing |  |
| 09:00 | 10:30 | Continued to trip in hole | Rig Repair |  |
| 10:30 | 24:00 | Drilled from 1898m to 1963m | Surveys |  |
|  |  |  | Run Casing |  |
|  |  |  | Rig Service |  |
|  |  |  | Test BOP’s | 1.00 |
|  |  |  | Drill Out Cement | 4.50 |
|  |  |  | Logging |  |
|  |  |  | W.O.C. |  |
|  |  |  | Cement Plug |  |
|  | JSA | Mixing hazardous chemicals | Wait on Cementer |  |
|  |  | Handling drill collars |  |  |
|  | 369 | Days Since Last LTA: |  |  |

| BIT INFORMATION | MUD PROPERTIES |
| --- | --- |
| Bit Number | 8 Run-12 | 13 Rerun-8 | Density (ppg) | 9.35 |
| Size (mm) | 156 | 156 | Viscosity (Sec) | 39 |
| Make | Reed | Reed | PV @ Degree C | 11 |
| Type | SL51HP | SL43HP | YP (lbs/100ft2) | 8 |
| IADC Code | 5-3-7 | 4-3-7 | API Filtrate (ml/30min) | 7.6 |
| Serial Number | HP5998 | JK4700 | Gels (lbs/100ft2) | 1 / 2 / 2 |
| Nozzles (x32) | 16-16-13 | 16-16-13 | Filter Cake (32nds inch) | 1/- |
| Depth In (m) | 1643 | 1898 | Sand (% Vol) | 0.10 / 0.25 |
| Depth Out (m) | 1898 |  | Solids (% Vol) | 7.9 |
| Total Metres | 251 | Previous 62m | Hardness (Ca mg/l) | 220 |
| Hours | 50.5 | 21.50 | KCl (% by wt) | 1.50 |
| WOB (kg) | 7000 | 8000 | Chlorides (Mg/l) | 9,500 |
| RPM | 100 | 90 | Methyl Blue (ppg eq) | 9.00 |
| Condition | 2-2-RG-G-E | In hole | Potassium (Mg/l) | 8,000 |
| Impact Force | 118lb/ft | 117lb/ft | Daily Cost ($) | 1,249 |
| Jet Velocity | 122 ft/sec | 122ft/sec | Cumulative Cost ($) | 46,399 |

LAKES OIL N.L.

DAILY DRILLING REPORT NO.                       PAGE: 2

| CEMENT DATA | LAST CASING | CHEMICALS USED |
| --- | --- | --- |
| Sacks |  | Size | 178 mm | Starlose | 2 |
| Class |  | Weight | 38.69 | Xanthum Gum XCD | 2 |
|  |  | Grade | N-80 | Defoamer | 2 |
|  |  | Connection | Buttress | Cepac-R | 4 |
|  |  | Joints | 92 | Potassium Chloride | 8 |
|  |  | Length | 1092.15m | AMC Biocide | 1 |
|  |  | Shoe | 1097.00 | Sodium Bicarbonate | 1 |
|  |  |  |  | Sodium Sulphite | 1 |

| SURVEYS | PUMP No.1 | PUMP No.2 |
| --- | --- | --- |
| 7.00 deg at | 1282 m | Liner | 140mm | Liner |  |
| 8.00 deg at | 1346 m | Stroke | 16 inch | Stroke |  |
| 8.00 deg at | 1387 m | Pressure | 8970kpa | Pressure |  |
| 8.50 deg at | 1415 m | A.V. DP | 192 ft/min | A.V. DP |  |
| 8.50 deg at | 1452 m | A.V. DC | 281 ft/min | A.V. DC |  |
| 9.00 deg at | 1489m m | SPM | 40 | SPM |  |
| 9.50 deg at | 1575 m | GPM | 198 | GPM |  |
| 7.9 deg at | 1880 m |  |  |  |  |
| deg at | m |  |  |  |  |

BHA: Bit-Bit sub- 2 x 4-3/4 Drill collars-Stabilizer-11 x 4-3/4 Drill collars-Jar-2 x 4-3/4 Drill collars

COMMENTS:

REPORT BY: Lou De-Vattimo