LAKES OIL N.L.

DAILY DRILLING REPORT

| WELL: Boundary Creek No.2 | REPORT No.: 35 | DATE: 13-11-2005 |
| --- | --- | --- |
| DFS: 34 | 2400 DEPTH: 2271m | Last Depth: 2193m |
| 24hr Progress: 78m | PTD: 2500m | Total Fuel: 5,600 |
| Fuel Usage: 1,800 | Daily Cost : 33,877 | Cum Cost: $1,736,192 |
| 0600hrs Operation: | 05:30am Wait on fishing tool for lost cone down hole Bit only drilled 78m in 21.5hrs |
| Next 24hr Operation: | Fish for Drill bit cone then continue to drill ahead with new Bit |
| Site Personnel: | Lakes 3, AMC 1, Higgins 2, Hunt 17 |

| HOURLY OPERATIONS SUMMARY (000-2400hrs) | OPERATIONS BREAKDOWN |
| --- | --- |
| FROM | TO | OPERATION | Drilling | 21.50 |
| 00:00 | 02:30 | Tripped in hole from 1073m to 2193m | Tripping | 2.50 |
| 02:30 | 24:00 | Drilled 152.4mm hole from 2193m to 2271m | Surveys |  |
|  |  |  | Reaming |  |
|  |  |  | Slip & Cut Block Line |  |
|  |  |  | Circulate & Clean Hole |  |
|  |  |  | Cement Casing |  |
|  |  |  | Rig Repair |  |
|  |  |  | Surveys |  |
|  |  |  | Run Casing |  |
|  |  |  | Rig Service |  |
|  |  |  | Test BOP’s |  |
|  |  |  | Drill Out Cement |  |
|  |  |  | Logging |  |
|  |  |  | W.O.C. |  |
|  |  |  | Cement Plug |  |
|  |  |  | Wait on Cementer |  |
|  |  |  | Make up Fishing Tools |  |

| BIT INFORMATION | MUD PROPERTIES |
| --- | --- |
| Bit Number | 5 | 6 | Density (ppg) | 9.65 |
| Run Number | 15 | 16 | Viscosity (Sec) | 43 |
| Size (mm) | 156 | 152.4 | PV @ Degree C | 16 |
| Make | Reed | Reed | YP (lbs/100ft2) | 14 |
| Type | SL53AK | SL43HKPR | API Filtrate (ml/30min) | 7.2 |
| IADC Code | 5-3-7 | 4-3-7 | Gels (lbs/100ft2) | 3/7/8 |
| Serial Number | NE2276 | HY2709 | Filter Cake (32nds inch) | 1/- |
| Nozzles (x32) | 13-14-16 | 13-14-16 | Sand (% Vol) | 0.10/0.25 |
| Depth In (m) | 2158 | 2193 | Solids (% Vol) | 8.6 |
| Depth Out (m) | 2193 |  | Hardness (Ca mg/l) | 280 |
| Total Meters | 35 | 78 | KCl (% by wt) | 1.83 |
| Hours | 15 | 21.50 | Chlorides (Mg/l) | 10,000 |
| WOB (kg) | 8,000 | 8,000 | Methyl Blue (ppg eq) | 10.0 |
| RPM | 90 | 90 | Potassium (Mg/l) | 9,300 |
| Condition | 0-0-N0-A-E-I | -NO-PR | Daily Cost ($) | 1,493 |
| Impact Force | 118lb/ft | 113lb/ft | Cumulative Cost ($) | 51,603 |
| Jet Velocity | 127ft/sec | 124ft/sec |  |  |

LAKES OIL N.L.

DAILY DRILLING REPORT NO.    35

| CEMENT DATA | LAST CASING | CHEMICALS USED |
| --- | --- | --- |
| Sacks |  | Size | 178mm | Starlose | 4 |
| Class |  | Weight | 38.69 | Xanthum Gum (XCD) | 1 |
|  |  | Grade | N-80 | Caustic | 1 |
|  |  | Connection | Buttress | Torque trim | 3 |
|  |  | Joints | 92 |  |  |
|  |  | Length | 1092.15m |  |  |
|  |  | Shoe | 1097.00m |  |  |
|  |  |  |  | AMC Defoamer | 2 |
|  |  |  |  | Sodium Sulphite | 2 |
|  |  |  |  | Liqisperse | 4 |
|  |  |  |  | Potassium Chloride | 9 |
|  |  |  |  | Sodium Bicarbonate | 2 |

| SURVEYS | PUMP No.1 | PUMP No.2 |
| --- | --- | --- |
| 9.5 degrees at 1575m | Liner | 140 mm | Liner |  |
| 7.9 degrees at 1880m | Stroke | 16 inch | Stroke |  |
| 8.0 degrees at 1956m | Pressure | 8,970 KPA | Pressure |  |
| 6.4 degrees at 2146m | A.V. DP | 192 ft/min | A.V. DP |  |
|  | A.V. DC | 281 ft/min | A.V. DC |  |
|  | SPM | 40 | SPM |  |
|  | GPM | 198 | GPM |  |

OCCUPATIONAL HEALTH AND SAFETY

| BHA: | Bit-Junk Sub - 2x4¾75” Drill Collars - 14x4¾” Drill Collars – Jars - 2x4¾” Drill Collars |
| --- | --- |
| DAYS SINCE LAST LTA: | 375 |
| COMMENTS: | Slow drill rate due to hard formation |
| REPORT BY: | Lou De-Vattimo |