LAKES OIL N.L.

DAILY DRILLING REPORT

| WELL: Boundary Creek No.2 | REPORT No.: 37 | DATE: 15-11-2005 |
| --- | --- | --- |
| DFS: 36 | 2400 DEPTH: 2288m | Last Depth: 2271m |
| 24hr Progress: 17m | PTD: 2500m | Total Fuel: 2,200lt |
| Fuel Usage: 1,400lt | Daily Cost : $31,542 | Cum Cost: $1,801,129 |
| 0600hrs Operation: | Drilling 152.4mm hole at 2295m |
| Next 24hr Operation: | Drill ahead |
| Site Personnel: | Lakes 3, AMC 1, Higgins 2, Hunt 19 |

| HOURLY OPERATIONS SUMMARY (000-2400hrs) | OPERATIONS BREAKDOWN |
| --- | --- |
| FROM | TO | OPERATION | Drilling | 10.50 |
| 00:00 | 02:00 | Tripped in hole from 1092-2259m with Bit # 7 | Tripping | 13.00 |
| 02:00 | 11:00 | Drilled from 2271m to 2285m | Surveys |  |
| 11:00 | 16:00 | Tripped out due to torque while drilling | Reaming |  |
| 16:00 | 22:00 | Changed bits then tripped in hole with Bit # 8 | Slip & Cut Block Line |  |
| 22:00 | 22:30 | Picked up Kelly then worked Junk sub on bottom | Circulate & Clean Hole | 0.50 |
| 22:30 | 24:00 | Drilled 152.4mm hole from 2285m to 2288m | Cement Casing |  |
|  |  |  | Rig Repair |  |
|  |  |  | Surveys |  |
|  |  |  | Run Casing |  |
|  |  |  | Rig Service |  |
|  |  |  | Test BOP’s |  |
|  |  |  | Drill Out Cement |  |
|  |  |  | Logging |  |
|  |  |  | W.O.C. |  |
|  |  |  | Cement Plug |  |
|  |  |  | Wait on Cementer |  |
|  |  |  | Make up Fishing Tools |  |

| BIT INFORMATION | MUD PROPERTIES |
| --- | --- |
| Bit Number | 7 | 8 | Density (ppg) | 9.55 |
| Run Number | 17 | 18 | Viscosity (Sec) | 41 |
| Size (mm) | 152.4 | 152.4 | PV @ Degree C | 14 |
| Make | Reed | Reed | YP (lbs/100ft2) | 11 |
| Type | SL12TKPR | SL53ADHTP | API Filtrate (ml/30min) | 7.4 |
| IADC Code | 1-2-7 | 5-3-7 | Gels (lbs/100ft2) | 2 / 4 / 6 |
| Serial Number | NR 2615 | MX8935 | Filter Cake (32nds inch) | 1/- |
| Nozzles (x32) | 13-14-16 | 13-14-20 | Sand (% Vol) | 0.10/0.25 |
| Depth In (m) | 2271 | 2285 | Solids (% Vol) | 9.0 |
| Depth Out (m) | 2285 |  | Hardness (Ca mg/l) | 80 |
| Total Meters | 17 |  | KCl (% by wt) | 1.58 |
| Hours | 9 |  | Chlorides (Mg/l) | 9,900 |
| WOB (kg) | 8,000 |  | Methyl Blue (ppg eq) | 9.0 |
| RPM | 90 |  | Potassium (Mg/l) | 8,400 |
| Condition | 2-2-BT-H-0-I | -LT-TQ | Daily Cost ($) | 775 |
| Impact Force | 96lb/ft |  | Cumulative Cost ($) | 52,507 |
| Jet Velocity | 103ft/sec |  |  |  |

LAKES OIL N.L.

DAILY DRILLING REPORT NO.    37

| CEMENT DATA | LAST CASING | CHEMICALS USED |
| --- | --- | --- |
| Sacks |  | Size | 178mm | AMC Defoamer | 2 |
| Class |  | Weight | 38.69 | Baracarb-25 | 10 |
|  |  | Joints | 92 | Barite | 10 |
|  |  | Length | 1092.15m | Caustic | 1 |
|  |  | Shoe | 1097.00m | Starlose | 7 |
|  |  |  |  | Sodium Bicarbonate | 1 |
|  |  |  |  | Sodium Sulphite | 2 |
| SURVEYS | PUMP No.1 | PUMP No.2 |
| 9.5 degrees at 1575m | Liner | 140 mm | Liner |  |
| 7.9 degrees at 1880m | Stroke | 16 inch | Stroke |  |
| 8.0 degrees at 1956m | Pressure | 8,970 KPA | Pressure |  |
| 6.4 degrees at 2146m | A.V. DP | 192 ft/min | A.V. DP |  |
|  | A.V. DC | 281 ft/min | A.V. DC |  |
|  | SPM | 38 | SPM |  |
|  | GPM | 188 | GPM |  |

OCCUPATIONAL HEALTH AND SAFETY

| BHA: | Bit-Junk Sub - 2x4¾75” Drill Collars - 14x4¾” Drill Collars – Jars - 2x4¾” Drill Collars |
| --- | --- |
| DAYS SINCE LAST LTA: | 377 |
| COMMENTS: | Slow drill rate due to hard formation |
| REPORT BY: | Lou De-Vattimo |