LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 4 | DFS: | 3 | DATE : | 13-Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 132 | LAST DEPTH : | 71.00m | 24 HR PROGRESS : | 61m | PTD : | 2500m |
| TOTAL FUEL : | 11,700 | FUEL USAGE : | 700 | DAYCOST : $ | 51,068 | CUM. COST : $ | 316,438 |
| 0600 OPS : | Drilling 311mm hole at 220m |
| Next 24 hr OPS: | Drill to 24 9 m then run 244mm Casing |
| Site Personnel: | Lakes 3- A.M.C 1- Mud logger 2- Hunt Energy 20 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 Re-Run |  |  | Drilling | 2.00 |  | Density | Spud mud | ppg |
| Size (mm) | 311 |  |  | Tripping | 2.5 |  | Viscosity |  | Sec |
| Make | BBL |  |  | Surveys |  |  | PV @ Deg C |  | Deg C |
| Type | M-22 |  |  | Reaming | 7.50 |  | YP lbs/100 ft 2 |  | Lbs/100ft |
| IADC Code | 1-1-7 |  |  | Slip and cut block line |  |  | API Filtrate |  | m/30min |
| Serial Number | 6093062 |  |  | Circulate and clean hole | 3.00 |  | Gels lbs/100 ft 2 |  |  |
| Nozzles (32) | 18-18-18 |  |  | Cement casing |  |  | Cake 32nds/ in |  |  |
| Depth in (m) | 15.00 |  |  | Rig repair |  |  | Sand |  | % Vol |
| Depth out (m) | In hole |  |  | Surveys |  |  | Solids |  | % Vol |
| Total Metres | 117 |  |  | Run Casing | 3.00 |  | Hardness Ca mg/l |  |  |
| Hours | 7 |  |  | Rig Service |  |  | KCL Concentration |  | % by wt |
| WOB (kg) | 1000 |  |  | Make up conductor pipe | 6.00 |  | Chlorides |  | Mg/l |
| RPM | 80 |  |  | Drill out Cmt |  |  | Methyl Blue |  | Ppb equiv |
| Condition |  |  |  | Logging |  |  | K+ |  | Mg/l |
| Impact Force | lb/ft |  |  | W.0.C |  |  | Daily Cost $ | 1,212 |
| Jet Velocity | ft/sec |  |  | Cement plug |  |  | Cum Cost $ | 5,845 |
| B.H.A.: | Bit- Bit sub- 2 X 8inch drill collars- crossover sub – 8 x 6-1/2 inch drill collars |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 00:00 |  | Reamed hole out from 311mm to 444mm from |  |  | ° at |  | m |  | Ausgel | 94 |
|  | 05:30 | surface to 58m |  |  | ° at |  | m |  | AMC Defoamer | 1 |
| 05:30 | 07:30 | Build up mud volume in pits |  |  | ° at |  | m |  | Calcium chloride | 6 |
| 07:30 | 09:30 | Reamed from 58m to 70m |  |  | ° at |  | m |  | Awdut | 0.5cubic m |
| 09:30 | 10;30 | Tripped out of hole |  |  | ° at |  | m |  |  |  |
| 10:30 | 11:30 | Rigged up to run 13-3/8 inch conductor casing |  |  | ° at |  | m |  |  |  |
| 11:30 | 13:30 | Ran 6 jnts of Casing to isolate the loss circulation zone |  |  | ° at | 1713 | m |  |  |  |
| 13:30 | 15:00 | Landed casing at 69m , unable to circulate |  |  |  |  |
| 15:00 |  | Rigged up the flowline – cemented around conductor |  | PUMP 1 |  | PUMP 2 |
|  | 20:30 | Pipe with 40 sax of cement |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 20;30 | 22:00 | Made up 311mm drilling assembly tripped in hole |  | Pressure | 1000 | kPa |  | Pressure |  | KPa |
| 22:00 | 24:00 | Drilled 311mm hole from 71m to 132m |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 50 |  | SPM |  |
|  |  |  |  | GPM | 250 |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 40 |  | Size | 340mm |  |
|  |  |  |  | Class |  |  | Weight | 71.43 | Kg/m |
|  |  |  |  |  |  |  |  | Grade | K-55 |  |
|  |  |  |  |  |  |  |  | Connection | Buttress |  |
|  |  |  |  |  |  |  |  | Joints | 6 |  |
|  |  |  |  |  |  |  |  | Length |  | m |
| Days since | LTA | 345 |  |  |  |  | Shoe | 69 | m |

,66