LAKES OIL N.L.

DAILY DRILLING REPORT

| WELL: Boundary Creek No.2 | REPORT No.: 44 | DATE: 22-11-2005 |
| --- | --- | --- |
| DFS: 43 | 2400 DEPTH: 2341m | Last Depth: 2341m |
| 24hr Progress: 0m | PTD: 2500m | Total Fuel: 4,500 |
| Fuel Usage: 600 | Daily Cost : $ 38,217 | Cum Cost: $2,121,174 |
| 0600hrs Operation: | Tagged top of Cement plug at 1070m with 10k/lbs |
| Next 24hr Operation: | Lay out drillpipe then set plug # 2 130m to surface |
| Site Personnel: | Lakes 2 , Hunt 17 , Baker Atlas 6 ,Halliburton 3 |

| HOURLY OPERATIONS SUMMARY (000-2400hrs) | OPERATIONS BREAKDOWN |
| --- | --- |
| FROM | TO | OPERATION | Drilling |  |
| 00:00 | 07:30 | Baker Atlas calibrated NMR tool | Tripping | 4.50 |
| 07:30 | 16:00 | Ran log # 6 | Surveys |  |
| 16:00 | 17:00 | Rigged down logger | Reaming |  |
| 17:00 | 20:00 | Tripped in hole to 1150m with open pipe | Slip & Cut Block Line |  |
| 20:00 | 21:00 | Rigged up Hallibuton held safety meeting | Circulate & Clean Hole | 1.00 |
| 21:00 | 22:00 | Circulated then tested cement lines | Cement Casing |  |
| 22:00 | 22:30 | Set cement plug from 1150m to 1050m | Rig Repair |  |
| 22:30 | 23:00 | Pulled back to 950m | Surveys |  |
| 23:00 | 24:00 | Layed out excess drill pipe while W.O.C | Run Casing |  |
|  |  |  | Rig Service |  |
|  |  |  | Test BOP’s |  |
|  |  |  | Drill Out Cement |  |
|  |  |  | Logging | 17.00 |
|  |  |  | W.O.C. |  |
|  |  |  | Cement Plug | 1.50 |
|  |  | Baker Atlas logging costs to be added | Wait on Cementer |  |
|  |  | Halliburton costs to be added | Make up Fishing Tools |  |

| BIT INFORMATION | MUD PROPERTIES |
| --- | --- |
| Bit Number |  |  | Density (ppg) | 9.40 |
| Run Number |  |  | Viscosity (Sec) | 44 |
| Size (mm) |  |  | PV @ Degree C | 15 |
| Make |  |  | YP (lbs/100ft2) | 14 |
| Type |  |  | API Filtrate (ml/30min) | 7.8 |
| IADC Code |  |  | Gels (lbs/100ft2) | 2 / 3 / 4 |
| Serial Number |  |  | Filter Cake (32nds inch) | 1/- |
| Nozzles (x32) |  |  | Sand (% Vol) | 0.10 |
| Depth In (m) |  |  | Solids (% Vol) | 7.9 |
| Depth Out (m) |  |  | Hardness (Ca mg/l) | 60 |
| Total Meters |  |  | KCl (% by wt) | 1.42 |
| Hours |  |  | Chlorides (Mg/l) | 9,700 |
| WOB (kg) |  |  | Methyl Blue (ppg eq) | 7.5 |
| RPM |  |  | Potassium (Mg/l) | 7,500 |
| Condition |  |  | Daily Cost ($) | 0 |
| Impact Force |  |  | Cumulative Cost ($) | 55,019 |
| Jet Velocity |  |  |  |  |

LAKES OIL N.L.

DAILY DRILLING REPORT NO.    43

| CEMENT DATA | LAST CASING | CHEMICALS USED |
| --- | --- | --- |
| Sacks |  | Size | 178mm |  |  |
| Class |  | Weight | 38.69 |  |  |
|  |  | Joints | 92 |  |  |
|  |  | Length | 1092.15m |  |  |
|  |  | Shoe | 1097.00m |  |  |
| SURVEYS | PUMP No.1 | PUMP No.2 |
| 9.5 degrees at 1575m | Liner | 140 mm | Liner |  |
| 7.9 degrees at 1880m | Stroke | 16 inch | Stroke |  |
| 8.0 degrees at 1956m | Pressure |  | Pressure |  |
| 6.4 degrees at 2146m | A.V. DP |  | A.V. DP |  |
|  | A.V. DC |  | A.V. DC |  |
|  | SPM |  | SPM |  |
|  | GPM |  | GPM |  |

| OCCUPATIONAL HEALTH AND SAFETY |
| --- |
| Running cement plugs |  |  |

| BHA: |  |
| --- | --- |
| DAYS SINCE LAST LTA: | 383 |
| COMMENTS: | Loaded out 10 Drill collars-5 HWDP-79 joints drill pipe to Perth ( Weatherford ) |
| REPORT BY: | Lou De-Vattimo |