LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 7 | DFS: | 6 | DATE : | 16-Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 509m | LAST DEPTH : | 261m | 24 HR PROGRESS : | 248m | PTD : | 2500m |
| TOTAL FUEL : | 12,100 | FUEL USAGE : | 800 |  | 46,117 | CUM. COST : $ | 452,764 |
| 0600 OPS : | Drilling 216mm hole at 580m |
| Next 24 hr OPS: | Drill to 600m – Survey -Wiper trip to shoe at 258m-Continue drilling |
| Site Personnel: | Lakes 3- A.M.C 1- Mud logger 2- Hunt Energy 20- Atlas loggers 3 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 2 Re run |  |  | Drilling | 16.50 |  | Density | 8.70 | ppg |
| Size (mm) | 216mm |  |  | Tripping | 3.00 |  | Viscosity | 37 | Sec |
| Make | Reed |  |  | Surveys |  |  | PV @ Deg C | 10 | Deg C |
| Type | ETH 11 |  |  | Reaming |  |  | YP lbs/100 ft 2 | 6 | Lbs/100ft |
| IADC Code | 1-1-7 |  |  | Slip and cut block line |  |  | API Filtrate | 7.5 | m/30min |
| Serial Number | MX-8867 |  |  | Circulate and clean hole |  |  | Gels lbs/100 ft 2 | 1/2/2 |  |
| Nozzles (32) | 13-13-13 |  |  | Cement casing |  |  | Cake 32nds/ in | <1 |  |
| Depth in (m) | 261 |  |  | Rig repair |  |  | Sand | 1.5 / .15 | % Vol |
| Depth out (m) |  |  |  | Surveys |  |  | Solids | 2.5 | % Vol |
| Total Metres | 248 |  |  | Run Casing |  |  | Hardness Ca mg/l | 540 |  |
| Hours | 16.50 |  |  | Rig Service |  |  | KCL Concentration | 1.25 | % by wt |
| WOB (kg) | 5000 |  |  | Test BOP | 2.50 |  | Chlorides | 7,600 | Mg/l |
| RPM | 90 |  |  | Drill out Cmt | 2.00 |  | Methyl Blue | 6.0 | Ppb equiv |
| Condition |  |  |  | Logging |  |  | K+ | 6,600 | Mg/l |
| Impact Force | 228 |  |  | W.0.C |  |  | Daily Cost $ | 2,595 |
| Jet Velocity | 205 |  |  | Cement plug |  |  | Cum Cost $ | 11,046 |
| B.H.A.: | Bit- Bit sub- 2 x 6-1/4inch drill collars- stabilizer -6 x 6-1/4inch drill collars -4 x Hevi-Wate drillpipe |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 0.25 | ° at | 218m | m |  | Type | Amount |
| 00:00 | 02:00 | Completed testing BOP - Choke manifold |  |  | ° at |  | m |  | Starlose | 10 |
| 02;00 | 05;00 | Made up 216mm Bit – R.I.H tagged cement at 252m |  |  | ° at |  | m |  | AMC Defoamer | 2 |
| 05:00 | 06:00 | Layed excess pipe from derrick-picked up the Kelly |  |  | ° at |  | m |  | AMC PAC-R | 4 |
| 06:00 | 07:00 | Drilled out shoetrack - 3 m of new hole 261m-264m |  |  | ° at |  | m |  | Sodium Sulphite | 1 |
| 07:00 | 07:30 | Leak off test at 264m with 8.55ppg mud 175psi |  |  | ° at |  | m |  | Potassium chloride | 18 |
| 07;30 | 24:00 | Drilled 216mm hole from 264m to 509m |  |  | ° at |  | m |  | Calcium Chloride | 11 |
|  |  |  |  |  | ° at |  | m |  | Ausgel / XCD | 2 / 2 |
|  |  | Leak off EMW a t 264m 12.5ppg |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 4550 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP | 117 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 183 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 50 |  | SPM |  |
|  |  |  |  | GPM | 250 |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks |  |  | Size | 244mm |  |
|  |  |  |  | Class |  |  | Weight | 53.57 | Kg/m |
|  |  |  |  |  |  |  |  | Grade | K-55 |  |
|  |  |  |  |  |  |  |  | Connection | Buttress |  |
|  | JSA | Mixing chemicals- BHA |  |  |  |  |  | Joints | 21 |  |
|  |  |  |  |  |  |  |  | Length | 253 | m |
| Days since | LTA | 348 |  |  |  |  | Shoe | 258 | m |

,66