LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 11 | DFS: | 10 | DATE : | 20-Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1082m | LAST DEPTH : | 956m | 24 HR PROGRESS : | 126m | PTD : | 2500m |
| TOTAL FUEL : | 12,100 | FUEL USAGE : | 2000 |  | 28,239 | CUM. COST : $ | 580,858 |
| 0600 OPS : | Prepare to trip out for logging |
| Next 24 hr OPS: | Trip out –log the well-trip back in hole –circulate-lay out the drilling assembly –run 7 inch casing |
| Site Personnel: | Lakes 4- A.M.C 1- Mud logger 2- Hunt Energy 18- Atlas loggers 6 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 2 Re run | 3 Re-run |  | Drilling | 24.00 |  | Density | 9.70 | ppg |
| Size (mm) | 216mm | 216mm |  | Tripping |  |  | Viscosity | 42 | Sec |
| Make | Reed | Reed |  | Surveys |  |  | PV @ Deg C | 11 | Deg C |
| Type | ETH 11 | TD43AKPR |  | Reaming |  |  | YP lbs/100 ft 2 | 11 | Lbs/100ft |
| IADC Code | 1-1-7 | 4-3-7 |  | Slip and cut block line |  |  | API Filtrate | 7.2 | m/30min |
| Serial Number | MX-8867 | RX6355 |  | Circulate and clean hole |  |  | Gels lbs/100 ft 2 | 3 / 9/ 10 |  |
| Nozzles (32) | 13-13-13 | 13-13-13 |  | Cement casing |  |  | Cake 32nds/ in | 1 |  |
| Depth in (m) | 261 | 947 |  | Rig repair |  |  | Sand | 0.10 / 0.20 | % Vol |
| Depth out (m) | 947 |  |  | Surveys |  |  | Solids | 10.3 | % Vol |
| Total Metres | 686 / 1024 | 135 |  | Run Casing |  |  | Hardness Ca mg/l | 100 |  |
| Hours | 58.50 / 114 | 25.50 |  | Rig Service |  |  | KCL Concentration | 1.42 | % by wt |
| WOB (kg) | 8000 | 8000 |  | Test BOP |  |  | Chlorides | 9,000 | Mg/l |
| RPM | 90 | 90 |  | Drill out Cmt |  |  | Methyl Blue | 15.00 | Ppb equiv |
| Condition | 3-3-FC-A-3-3-RG-TQ |  |  | Logging |  |  | K+ | 7,500 | Mg/l |
| Impact Force | 444 |  |  | W.0.C |  |  | Daily Cost $ | 3,122 |
| Jet Velocity | 270 |  |  | Cement plug |  |  | Cum Cost $ | 20,339 |
| B.H.A.: | Bit- Bit sub- 2 x 6-1/4inch drill collars- stabilizer -6 x 6-1/4inch drill collars -4 x Hevi-Wate drillpipe |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 0.25 | ° at | 218m | m |  | Type | Amount |
| 00:00 | 24:00 | Drilled 216mm hole from 956m to 1082m |  | 1.50 | ° at | 600m | m |  | Starlose / Caustic | 12 / 4 |
|  |  |  |  | 2.00 | ° at | 797m | m |  | AMC Defoamer | 4 |
|  |  |  |  | 2.50 | ° at | 938m | m |  | AMC PAC-L | 6 |
|  |  |  |  |  | ° at |  | m |  | Sod Sulphite / Bar | 2 / |
|  |  |  |  |  | ° at |  | m |  | Potassium chloride | 8 |
|  |  |  |  |  | ° at |  | m |  | Soium Bicarbonate | 6 |
|  |  |  |  |  | ° at |  | m |  | Liqui-sperse | 4 |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 6,300 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP | 154 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 241 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 66 |  | SPM |  |
|  |  |  |  | GPM | 327 |  | GPM |  |
|  |  | Hauled 22 jnts 7 inch Casing from Dyers yard to site |  |  |  |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks |  |  | Size | 244mm |  |
|  |  |  |  | Class |  |  | Weight | 53.57 | Kg/m |
|  |  |  |  |  |  |  |  | Grade | K-55 |  |
|  |  |  |  |  |  |  |  | Connection | Buttress |  |
|  | JSA | Greasing the crown- Checking brake linkages |  |  |  |  |  | Joints | 21 |  |
|  |  |  |  |  |  |  |  | Length | 253 | m |
| Days since | LTA | 352 |  |  |  |  | Shoe | 258 | m |

,66