LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 14 | DFS: | 13 | DATE : | 23 Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1100m | LAST DEPTH : | 1100m | 24 HR PROGRESS : | 0m | PTD : | 2500m |
| TOTAL FUEL : | 8,600 | FUEL USAGE : | 800 |  | 276,062 | CUM. COST : $ | 907,999 |
| 0600 OPS : | Continue to make up wellhead spools |
| Next 24 hr OPS: | Make up the “B” Section to BOP then test same- Pick up 156mm drilling assembly and run in hole to drill out shoetrack |
| Site Personnel: | Lakes 3 A.M.C 1- Mud logger 2- Hunt Energy 18- Atlas loggers 6 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number |  |  |  | Drilling |  |  | Density |  | ppg |
| Size (mm) |  |  |  | Tripping | 1.00 |  | Viscosity |  | Sec |
| Make |  |  |  | Surveys |  |  | PV @ Deg C |  | Deg C |
| Type |  |  |  | Reaming |  |  | YP lbs/100 ft 2 |  | Lbs/100ft |
| IADC Code |  |  |  | Slip and cut block line |  |  | API Filtrate |  | m/30min |
| Serial Number |  |  |  | Circulate and clean hole |  |  | Gels lbs/100 ft 2 |  |  |
| Nozzles (32) |  |  |  | Cement casing |  |  | Cake 32nds/ in |  |  |
| Depth in (m) |  |  |  | Rig repair | 1.00 |  | Sand |  | % Vol |
| Depth out (m) |  |  |  | Surveys |  |  | Solids |  | % Vol |
| Total Metres |  |  |  | Run Casing | 12.00 |  | Hardness Ca mg/l |  |  |
| Hours |  |  |  | Rig Service |  |  | KCL Concentration |  | % by wt |
| WOB (kg) |  |  |  | Test BOP |  |  | Chlorides |  | Mg/l |
| RPM |  |  |  | Drill out Cmt |  |  | Methyl Blue |  | Ppb equiv |
| Condition |  |  |  | Logging |  |  | K+ |  | Mg/l |
| Impact Force |  |  |  | W.0.C | 6.00 |  | Daily Cost $ | 1,345 |
| Jet Velocity |  |  |  | Install BOP | 4.00 |  | Cum Cost $ | 25,654 |
| B.H.A.: | Bit- Bit sub- 2 x 6-1/4inch drill collars- stabilizer -6 x 6-1/4inch drill collars-Jars-2 x 6-1/4 inch drill collars -4 x Hevi-Wate drillpipe |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 0.25 | ° at | 218m | m |  | Type | Amount |
| 00:00 | 01:00 | Layed out drill string |  | 1.50 | ° at | 600m | m |  | Defoamer / Biocide | 2 / 1 |
| 01:00 | 02:00 | Rigged up for running casing |  | 2.00 | ° at | 797m | m |  |  |  |
| 02:00 | 03:00 | Repaired the casing tong rotation lever |  | 2.50 | ° at | 938m | m |  | AMC PAC-L / R | 3 / 1 |
| 03:00 | 09:30 | Ran casing 92 joints with shoe at 1097m |  | 3.00 | ° at | 1096m | m |  | Starlose | 1 |
| 09:30 | 10;30 | Rigged up Halliburton then circulated |  |  | ° at |  | m |  | Potassium chloride | 6 |
| 10:30 | 11:00 | Held safety meeting then pressure tested lines |  |  | ° at |  | m |  | Soium Bicarbonate |  |
| 11:00 | 12:00 | Cemented the casing bumped plug held good |  |  | ° at |  | m |  | Sodium sulphite | 1 |
| 12:00 | 18:00 | W.O.C |  |  |  |  |
| 18:00 | 24:00 | Raised BOP to install Casing slips and “B” Section |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure |  | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM |  |
|  |  |  |  | GPM |  |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks |  |  | Size | 178mm |  |
|  |  |  |  | Class |  |  | Weight | 38.69 | Kg/m |
|  |  |  |  |  |  |  |  | Grade | N-80 |  |
|  |  |  |  |  |  |  |  | Connection | Buttress |  |
|  | JSA |  |  |  |  |  |  | Joints | 92 |  |
|  |  |  |  |  |  |  |  | Length |  | m |
| Days since | LTA | 355 |  |  |  |  | Shoe | 1097 | m |

,66