## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-09-24
6
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 765 |  |  | 24 HR PROG | 214.999 |  |  |  | CUM. COSTS | 1715431.62
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Dilwyn | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 100121.22
OP's TO 06:00 |  | Drill 8 1/2" hole from 765m to 924m.
REMARKS: |  | Take Anderdrift surveys every 30m, all surveys to 6am zero. | [10 empty] | PERSONNEL ON SITE: |  |  | 0
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  | 536.0661 |  |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
58 |  | SAFETY | 1. Winch operation/ BHA handling/ tool box talks | [10 empty] | WEATHER AM | Cloudy/Cold
|  |  | 2. Alerts/near miss on rig 3/ DC in derrick/ Single joint p/ups. | [10 empty] | PM | Cloudy/Cold
BIT INFORMATION |  |  |  | 2 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 5-10 | JET V(fps) | 243.3309 | TOOL |  |  | LENGTH |  | Time | 2400 |  |  | Casing |  |  | 8
RPM | 120 | H S I | 2.8524 | Bit |  |  | 0.27 |  | Depth (m) | 765 |  |  | Cementing |  |  | 1.5
BIT NUMBER |  | 2 | 0 | Near Bit Stab |  |  | 1.27 |  | Temp (° C) | 37 |  |  | Circ & Condition |  |  | 3
Size (in) |  | 8.5 |  | Ander drift |  |  | 3.01 |  | Mud Type | KCL/PHPA |  |  | Coring |  |  | 0
Make |  | Hughes |  | Drill collars x 1 |  |  | 9.18 |  | Density (ppg) | 8.65 |  |  | D/O Cement |  | 2 | 2
Type |  | HC605S |  | String Stab |  |  | 1.35 |  | ECD (ppg) | 9.0931 |  |  | Drilling |  | 7.5 | 33.5
IADC Code |  | M223 |  | Drill collars x 14 |  |  | 129.26 |  | Viscosity (sec) | 47 |  |  | Handle BHA |  | 4 | 4
Serial Number |  | 7002589 |  | Drilling Jars |  |  | 9.56 |  | PV / YP (cp/lb) | 12 / 18 |  |  | LOT / FIT |  | 0.5 | 0.5
T.F.A.( ") |  | 0.79844 |  | Drill Collar x 2 |  |  | 18.04 |  | Gells (s/m) | 7 / 9 |  |  | N/U & Test BOP's |  | 2 | 43.5
Depth In (m) |  | 550 |  | Hwdp x 4 |  |  | 37.55 |  | API Filt. (cc) | 7 |  |  | P & A |  |  | 0
Depth Out (m) |  | IN | [6 empty] | Cake (/32") | 1 |  |  | Repairs |  | 4.5 | 4.5
Total Meters |  | 215 | [6 empty] | Solids (% Vol) | 6 |  |  | Rig Move |  |  | 18
Hours |  | 7.5 | [6 empty] | Sand (% Vol) | 0.75 |  |  | Rig Service |  |  | 1
ROP |  | 28.6667 | [6 empty] | MBT | 3 |  |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 209.49 |  | pH (strip) | 9.5 |  |  | Survey |  |  | 0
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 44.6443 |  | Chlorides (mg/l) | 22000 |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 605.5114 |  | STRING WT (kLb) |  |  | 74.4585 |  | KCL (% ) | 4.2 |  |  | Tripping |  | 2 | 6
AV - DP (fpm) |  | 285.4055 |  | HOOK LOAD (kLb) |  |  | 90 |  | PHPA (ppb) | 0.75 |  |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 447.189 |  | WT BELOW JARS (kLb) |  |  | 34.1733 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  |  | 0
SPP (psi) |  | 1100 |  | DRAG UP (kLb) |  |  | 5 |  | Circ. Vol. (Bbl) | 405 |  |  | Well Control |  |  | 0
SPP (calculated) |  | 1000 |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 0-50 |  | Defoam |  | 1 |  | Wellhead |  | 1 | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  | 0 |  | Duo-Tec |  | 6 |  | Wiper Trip |  |  | 5
RATE | 100 | RATE | 100 | ENVIRONMENTAL DATA |  |  |  |  | Glute 25 |  | 1 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 33150 |  |  | Kwikseal F |  | 34 |  | Other |  | 0.5 | 1.5
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 1800 |  |  | Polyplus |  | 8 |  | TOTALS |  | 24 | 144
SCR: 250 @ 70 |  | SCR: 400 @ 100 |  | CUM. FUEL USED |  | 16800 |  |  | Polypac UL |  | 5 |  | DAILY MUD COSTS |  | 6791.22
SURVEYS |  |  |  | CUM. MUD MIXED |  | 1934 |  |  | Sod Bicarb |  | 2 |  | CUM. MUD COSTS |  | 21370.62
0° at 580m |  | 0° at 700m |  | CUM. MUD LOSSES |  | 1819 |  |  | Pot chloride/KCL |  | 90 |  | AFE COST - C&S |  | 2847416
0° at 610m |  | 0° at 760m |  | CUM. GEL |  | 6000 | [6 empty] | AFE COST - P&A |  | 2588872
0° at 640m |  | 0° at 820m |  | CUM. BARITES |  | 0 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 2:00 | Complete testing of Choke valves and wing valves. Check all hydraulic connections on Bops.
2:00 | 3:00 | Make up and run wear bushing,
3:00 | 3:30 | Clean up rig floor of all Nipple up equipment, excess equipment
3:30 | 7:30 | Make up 8 1/2" bha
7:30 | 9:30 | RIH 8 1/2" drilling bha on 4 1/2" drill pipe, tag cmt at 523m
9:30 | 14:00 | Wait on #1 mud pump repairs. Second hand module fitted to #1 mud pump.
14:00 | 16:00 | Drill cement/ Flt collar/ shoe/ shoe track to 550m
16:00 | 16:30 | Drill 3m of new formation from 550m to 553m
16:30 | 17:00 | Complete FIT. EMW 14.4ppg. 544.5m TVD shoe,
17:00 | 24:00 | Drill 8 1/2" hole from 553m to 765m, survey @30m intervals with Anderdrift.
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #6