## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-09-26
8
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 1742 |  |  | 24 HR PROG | 415 |  |  |  | CUM. COSTS | 1821992.09
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Paarette | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 52901.52
OP's TO 06:00 |  | Continue to drill 8 1/2" hole from 1742m to 1815m
REMARKS: |  | Held BOP drills with both crews, flow check all drilling breaks. | [10 empty] | PERSONNEL ON SITE: |  |  | 37
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  | 503.5537 |  |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
60 |  | SAFETY | 1. Hydraulic winch operations. Benefits of tool box talks | [10 empty] | WEATHER AM | Fine/Cold
|  |  | 2. Discuss BOP drills | [10 empty] | PM | Cloudy/Cold
BIT INFORMATION |  |  |  | 2 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 10-15 | JET V(fps) | 243.3309 | TOOL |  |  | LENGTH |  | Time | 24:00 |  |  | Casing |  |  | 8
RPM | 90-120 | H S I | 2.9678 | Bit |  |  | 0.27 |  | Depth (m) | 1742 |  |  | Cementing |  |  | 1.5
BIT NUMBER |  | 2 | 0 | Near Bit Stab |  |  | 1.27 |  | Temp (° C) | 53 |  |  | Circ & Condition |  |  | 3
Size (in) |  | 8.5 |  | Ander drift |  |  | 3.01 |  | Mud Type | KCL/PHPA |  |  | Coring |  |  | 0
Make |  | Hughes |  | Drill collars x 1 |  |  | 9.18 |  | Density (ppg) | 9 |  |  | D/O Cement |  |  | 2
Type |  | HC605S |  | String Stab |  |  | 1.35 |  | ECD (ppg) | 9.7931 |  |  | Drilling |  | 23 | 80
IADC Code |  | S323 |  | Drill collars x 14 |  |  | 129.26 |  | Viscosity (sec) | 61 |  |  | Handle BHA |  |  | 4
Serial Number |  | 7002589 |  | Drilling Jars |  |  | 9.56 |  | PV / YP (cp/lb) | 23 / 31 |  |  | LOT / FIT |  |  | 0.5
T.F.A.( ") |  | 0.79844 |  | Drill Collar x 2 |  |  | 18.04 |  | Gells (s/m) | 9 / 13 |  |  | N/U & Test BOP's |  |  | 43.5
Depth In (m) |  | 550 |  | Hwdp x 4 |  |  | 37.55 |  | API Filt. (cc) | 5.5 |  |  | P & A |  |  | 0
Depth Out (m) |  | IN | [6 empty] | Cake (/32") | 1 |  |  | Repairs |  |  | 4.5
Total Meters |  | 1192 | [6 empty] | Solids (% Vol) | 8 |  |  | Rig Move |  |  | 18
Hours |  | 54 | [6 empty] | Sand (% Vol) | 0.5 |  |  | Rig Service |  | 1 | 2
ROP |  | 22.0741 | [6 empty] | MBT | 5 |  |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 209.49 |  | pH (strip) | 8.7 |  |  | Survey |  |  | 0.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 44.3688 |  | Chlorides (mg/l) | 22000 |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 605.5114 |  | STRING WT (kLb) |  |  | 126.1112 |  | KCL (% ) | 4.2 |  |  | Tripping |  |  | 6
AV - DP (fpm) |  | 285.4055 |  | HOOK LOAD (kLb) |  |  | 143 |  | PHPA (ppb) | 1.4 |  |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 447.189 |  | WT BELOW JARS (kLb) |  |  | 33.9624 |  | ALC - 50 (K) | 0.22 |  |  | Wash / Ream |  |  | 0
SPP (psi) |  | 1750 |  | DRAG UP (kLb) |  |  | 5 |  | Circ. Vol. (Bbl) | 795 |  |  | Well Control |  |  | 0
SPP (calculated) |  | 1800 |  | DRAG DOWN (kLb) |  |  | 5 |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 0-30 |  | Duo-Tec |  | 2 |  | Wellhead |  |  | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  |  |  | Glute 25 |  | 1 |  | Wiper Trip |  |  | 5
RATE | 100 | RATE | 100 | ENVIRONMENTAL DATA |  |  |  |  | Polyplus |  | 13 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 23400 |  |  | Polypac UL |  | 35 |  | Other |  |  | 1.5
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 5150 |  |  | Sod Bicarb |  | 3 |  | TOTALS |  | 24 | 192
SCR: 540 @ 70 |  | SCR: 760 @ 100 |  | CUM. FUEL USED |  | 26550 |  |  | Pot chloride/KCL |  | 128 |  | DAILY MUD COSTS |  | 9571.52
SURVEYS |  |  |  | CUM. MUD MIXED |  | 2794 |  |  | OS-1/Sod Sulphite |  | 4 |  | CUM. MUD COSTS |  | 40271.09
0° at 1373m |  | 0° at 1457m |  | CUM. MUD LOSSES |  | 2392 | [6 empty] | AFE COST - C&S |  | 2847416
0.5° at 1393m |  | 0° at 1654m |  | CUM. GEL |  | 6000 | [6 empty] | AFE COST - P&A |  | 2588872
0.5° at 1438m |  | 0.5° at 1740m |  | CUM. BARITES |  | 0 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 4:30 | Drill 8 1/2" hole from 1327m to 1421m, survey @ 30m intervals with Anderdrift. 1/2 degree at 1393m, others zero degrees
4:30 | 5:00 | Work on No 2 pump
5:00 | 16:30 | Drill 8 1/2" hole from 1421m to 1546m, survey @ 30m intervals with Anderdrift.
16:30 | 17:00 | Change out cap seal on number 2 mud pump
17:00 | 24:00 | Drill 8 1/2" hole from 1546m to 1742, survey @ 30m intervals with Anderdrift. 1/2 degree at 1740m,
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #8