## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-09-28
10
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 2246 |  |  | 24 HR PROG | 188 |  |  |  | CUM. COSTS | 1930477.87
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Belfast M/Stone | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 50581.49
OP's TO 06:00 |  | Circ btms up from shoe. Slip Drilling line. Service Blocks and drilling equipment. RIH to 2120m. Hole ok,
REMARKS: |  | Change out suction module on Mud pump #2. | [10 empty] | PERSONNEL ON SITE: |  |  | 36
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  | 503.5537 |  |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
62 |  | SAFETY | 1. Drilling ahead, H/Keeping on mud tanks | [10 empty] | WEATHER AM | Showers
|  |  | 2. POOH. Racking back pipe | [10 empty] | PM | Rain
BIT INFORMATION |  |  |  | 2 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 10-15 | JET V(fps) | 218.9978 | TOOL |  |  | LENGTH |  | Time | 20:00 |  |  | Casing |  |  | 8
RPM | 100 | H S I | 2.1635 | Bit |  |  | 0.27 |  | Depth (m) | 2246 |  |  | Cementing |  |  | 1.5
BIT NUMBER |  | 2 | 0 | Near Bit Stab |  |  | 1.27 |  | Temp (° C) |  |  |  | Circ & Condition |  | 1 | 4
Size (in) |  | 8.5 |  | Ander drift |  |  | 3.01 |  | Mud Type | KCL/PHPA |  |  | Coring |  |  | 0
Make |  | Hughes |  | Drill collars x 1 |  |  | 9.18 |  | Density (ppg) | 9 |  |  | D/O Cement |  |  | 2
Type |  | HC605S |  | String Stab |  |  | 1.35 |  | ECD (ppg) | 9.7132 |  |  | Drilling |  | 13 | 114.5
IADC Code |  | S323 |  | Drill collars x 14 |  |  | 129.26 |  | Viscosity (sec) | 60 |  |  | Handle BHA |  |  | 4
Serial Number |  | 7002589 |  | Drilling Jars |  |  | 9.56 |  | PV / YP (cp/lb) | 25 / 34 |  |  | LOT / FIT |  |  | 0.5
T.F.A.( ") |  | 0.79844 |  | Drill Collar x 2 |  |  | 18.04 |  | Gells (s/m) | 6 / 11 |  |  | N/U & Test BOP's |  |  | 43.5
Depth In (m) |  | 550 |  | Hwdp x 4 |  |  | 37.55 |  | API Filt. (cc) | 4.8 |  |  | P & A |  |  | 0
Depth Out (m) |  | IN | [6 empty] | Cake (/32") | 1 |  |  | Repairs |  | 0.5 | 6
Total Meters |  | 1696 | [6 empty] | Solids (% Vol) | 11 |  |  | Rig Move |  |  | 18
Hours |  | 88.5 | [6 empty] | Sand (% Vol) | 0.5 |  |  | Rig Service |  |  | 2.5
ROP |  | 19.1638 | [6 empty] | MBT | 10 |  |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 209.49 |  | pH (strip) | 8.7 |  |  | Survey |  |  | 1.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 44.3688 |  | Chlorides (mg/l) | 22000 |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 544.9602 |  | STRING WT (kLb) |  |  | 152.9941 |  | KCL (% ) | 4 |  |  | Tripping |  | 9.5 | 15.5
AV - DP (fpm) |  | 256.8649 |  | HOOK LOAD (kLb) |  |  | 153 |  | PHPA (ppb) | 1.25 |  |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 402.4701 |  | WT BELOW JARS (kLb) |  |  | 33.9624 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  |  | 0
SPP (psi) |  | 2100 |  | DRAG UP (kLb) |  |  | 5 |  | Circ. Vol. (Bbl) | 599 |  |  | Well Control |  |  | 0
SPP (calculated) |  | 1820 |  | DRAG DOWN (kLb) |  |  | 2 |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 0-40 |  | Barite |  | 40 |  | Wellhead |  |  | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  | 50-150 |  | Duo-Tec |  | 4 |  | Wiper Trip |  |  | 5
RATE | 90 | RATE | 90 | ENVIRONMENTAL DATA |  |  |  |  | Glute 25 |  | 3 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 34500 |  |  | Polypac UL |  | 21 |  | Other |  |  | 1.5
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 5300 |  |  | Sod Bicarb |  | 3 |  | TOTALS |  | 24 | 240
SCR: 650 @ 70 |  | SCR: 980 @ 100 |  | CUM. FUEL USED |  | 37700 |  |  | Pot chloride/KCL |  | 100 |  | DAILY MUD COSTS |  | 6551.49
SURVEYS |  |  |  | CUM. MUD MIXED |  | 3713 |  |  | OS-1/Sod Sulphite |  | 4 |  | CUM. MUD COSTS |  | 60396.87
1° at 2093m |  | 2.5° at 2186m |  | CUM. MUD LOSSES |  | 3394 | [6 empty] | AFE COST - C&S |  | 2847416
1° at 2149m |  | 3.5° at 2215m |  | CUM. GEL |  | 6000 | [6 empty] | AFE COST - P&A |  | 2588872
3° at 2177m |  | 3.5° at 2244m |  | CUM. BARITES |  | 1000 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 4:00 | Drill 8-1/2" hole from 2058 to 2114m - A/drift surveys: 1 deg at 2065 & 2093m
4:00 | 4:30 | Replace swab in No 1 pump
4:30 | 13:30 | Drill 8 1/2" hole f/ 2114m to 2246m. A/drift surveys at: 1 deg @2121, @2149m, 3 deg @2177, 2.5 @2186, 3.5 @2215 & 2244m
13:30 | 14:00 | Circulate hole clean
14:00 | 14:30 | Flow check, pump slug & pick up elevators
14:30 | 21:00 | POOH from 2246m. Hole good up to 1731m then tight with 10 - 30 klbs overpull until 1240m.
21:00 | 24:00 | Cont to POOH from 1240m with 5-15k overpull to 528m. Work slip area twice , no overpull on second wipe
Max overpull on trip out 30klbs. Once hole was wiped once then the string passed at neutral string wt.
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #10