## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-09-29
11
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 2377 |  |  | 24 HR PROG | 131 |  |  |  | CUM. COSTS | 1978719.45
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Waare | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 48241.58
OP's TO 06:00 |  | Continue to drill 8 1/2" hole from 2377m to 2451m
REMARKS: |  | Top Amplitude at 2335m | [10 empty] | PERSONNEL ON SITE: |  |  | 34
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  | 466.3967 |  |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
63 |  | SAFETY | 1. Slip line & run in hole | [10 empty] | WEATHER AM | Rain/wind/fine
|  |  | 2. Discuss general housekeeping | [10 empty] | PM | Rain/wind/fine
BIT INFORMATION |  |  |  | 2 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 10-18 | JET V(fps) | 204.3979 | TOOL |  |  | LENGTH |  | Time | 24:00 |  |  | Casing |  |  | 8
RPM | 100 | H S I | 1.8372 | Bit |  |  | 0.27 |  | Depth (m) | 2377 |  |  | Cementing |  |  | 1.5
BIT NUMBER |  | 2 | 0 | Near Bit Stab |  |  | 1.27 |  | Temp (° C) | 58 |  |  | Circ & Condition |  | 0.5 | 4.5
Size (in) |  | 8.5 |  | Ander drift |  |  | 3.01 |  | Mud Type | KCL/PHPA |  |  | Coring |  |  | 0
Make |  | Hughes |  | Drill collars x 1 |  |  | 9.18 |  | Density (ppg) | 9.4 |  |  | D/O Cement |  |  | 2
Type |  | HC605S |  | String Stab |  |  | 1.35 |  | ECD (ppg) | 10.1025 |  |  | Drilling |  | 14 | 128.5
IADC Code |  | S323 |  | Drill collars x 14 |  |  | 129.26 |  | Viscosity (sec) | 66 |  |  | Handle BHA |  |  | 4
Serial Number |  | 7002589 |  | Drilling Jars |  |  | 9.56 |  | PV / YP (cp/lb) | 27 / 34 |  |  | LOT / FIT |  |  | 0.5
T.F.A.( ") |  | 0.79844 |  | Drill Collar x 2 |  |  | 18.04 |  | Gells (s/m) | 6 / 10 |  |  | N/U & Test BOP's |  |  | 43.5
Depth In (m) |  | 550 |  | Hwdp x 4 |  |  | 37.55 |  | API Filt. (cc) | 5 |  |  | P & A |  |  | 0
Depth Out (m) |  | IN | [6 empty] | Cake (/32") | 1 |  |  | Repairs |  |  | 6
Total Meters |  | 1827 | [6 empty] | Solids (% Vol) | 8 |  |  | Rig Move |  |  | 18
Hours |  | 102.5 | [6 empty] | Sand (% Vol) | 0.6 |  |  | Rig Service |  | 1 | 3.5
ROP |  | 17.8244 | [6 empty] | MBT | 10 |  |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 209.49 |  | pH (strip) | 9.5 |  |  | Survey |  |  | 1.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 44.054 |  | Chlorides (mg/l) | 26000 |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 508.6296 |  | STRING WT (kLb) |  |  | 158.8464 |  | KCL (% ) | 4.3 |  |  | Tripping |  | 5 | 20.5
AV - DP (fpm) |  | 239.7406 |  | HOOK LOAD (kLb) |  |  | 180 |  | PHPA (ppb) | 1 |  |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 375.6387 |  | WT BELOW JARS (kLb) |  |  | 33.7215 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  | 3.5 | 3.5
SPP (psi) |  | 1900 |  | DRAG UP (kLb) |  |  | 3 |  | Circ. Vol. (Bbl) | 868 |  |  | Well Control |  |  | 0
SPP (calculated) |  | 1800 |  | DRAG DOWN (kLb) |  |  | 3 |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 0-40 |  | Barite |  | 176 |  | Wellhead |  |  | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  | 40-150 |  | Caustic Soda |  | 5 |  | Wiper Trip |  |  | 5
RATE | 84 | RATE | 84 | ENVIRONMENTAL DATA |  |  |  |  | Duo-Tec |  | 3 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 31400 |  |  | Glute 25 |  | 1 |  | Other |  |  | 1.5
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 3100 |  |  | Polyplus |  | 4 |  | TOTALS |  | 24 | 264
SCR: 600 @ 70 |  | SCR: 920 @ 100 |  | CUM. FUEL USED |  | 40800 |  |  | Sod Bicarb |  | 1 |  | DAILY MUD COSTS |  | 3811.58
SURVEYS |  |  |  | CUM. MUD MIXED |  | 3880 |  |  | Pot chloride/KCL |  | 43 |  | CUM. MUD COSTS |  | 64208.45
3° at 2280m |  | 3° at 2349m |  | CUM. MUD LOSSES |  | 3453 | [6 empty] | AFE COST - C&S |  | 2847416
3° at 2290m |  | 3° at 2377m |  | CUM. GEL |  | 6000 | [6 empty] | AFE COST - P&A |  | 2588872
3° at 2318m |  | 2.5° at 2433m |  | CUM. BARITES |  | 5400 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 0:30 | Circulate btms up from shoe.
0:30 | 1:00 | Slip drilling line
1:00 | 1:30 | Service Rig and drilling equipment, Shut down draw works motors and check all drive shaft universals
1:30 | 6:30 | RIH from 528m to 2120m
6:30 | 10:00 | Wash & ream to bottom, laid out singles & washed them down
10:00 | 24:00 | Drill 8-1/2" hole from 2246m to 2377m. Flow check drilling breaks @ 2335, 2360m.
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #11