Culverin-1

| Date: | 7-01-2006 | Last Casing: | 340 mm (13 3/8”) @ 1511.14 mMDRT |
| --- | --- | --- | --- |
| Report Number: | 19 | Leak Off Test: | 1.89 sg EMW @ 1528.0 mMDRT |
| Report Period: | 24hrs to 24:00 | Current hole size: | 311 mm (12 1/4”) |
| Depth @ 2400 Hrs: | 3758.0 mMDRT (TD) | Mud Weight: | 1.21 sg |
| Last Depth: | 3758.0 mMDRT | ECD: | n/a wireline logging |
| Progress: | 0 m | Mud Type: | KCl-NaCl-Polymer |
| TD Lithology: | Siltstone and minor Sandstone. | Mud Chlorides: | 79, 000 ppm |
| Water Depth: | 585.0 m | Mud Fluid Loss: | 3.8 cc |
| RT Elevation: | 21.5 m | Bit Type: | n/a wireline logging |

OPERATIONS SUMMARY

| 24 HOUR SUMMARY 00:00 - 24:00: | Reached TD 3758.0 mMDRT at 24:00 hrs on the 6-01-06. Pulled out to wipe/re-log section from 3575.0 – 3630.0 mMDRT with LWD tools. POOH. Remove nuclear sources from LWD, down load data and lay out LWD tools. Rig up for wireline logging. Run into the hole, Run (1) PEX-HALS-DSI-GR. |
| --- | --- |
| 06:00 Update | Commence rigging up tools for Wireline Run (2) VSI-4-GR. |
| NEXT 24 HOURS: | Continue wireline logging program. Run (2) VSI-4 |

GEOLOGICAL SUMMARY

- LITHOLOGIC DESCRIPTION:

| Interval mMDRT | Description |
| --- | --- |
| No drilling |  |

- HYDROCARBON FLUORESCENCE:

| INTERVAL (mMDRT) | FLUORESCENCE |
| --- | --- |
| No drilling |  |

- GAS SUMMARY:

| INTERVAL (mMDKB) | Total GAS (%) | C1 (ppm) | C2 (ppm) | C3 (ppm) | IC4 (ppm) | NC4 (ppm) | C5 (ppm) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No drilling |  |  |  |  |  |  |  |

- SURVEYS

| MD | ANGLE | Azi |  | MD | ANGLE | Azi |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2743.83 | 3.80 | 42.10 |  | 3375.03 | 3.69 | 54.03 |  |  |
| 2772.65 | 3.83 | 43.73 |  | 3404.40 | 3.54 | 54.90 |  |  |
| 2801.66 | 3.84 | 42.76 |  | 3432.80 | 3.59 | 51.96 |  |  |
| 2830.44 | 3.89 | 43.81 |  | 3461.32 | 3.48 | 51.53 |  |  |
| 2859.14 | 3.95 | 44.31 |  | 3490.24 | 3.38 | 50.31 |  |  |
| 2887.70 | 3.86 | 45.65 |  | 3519.26 | 3.32 | 50.11 |  |  |
| 2916.43 | 3.87 | 45.26 |  | 3547.59 | 3.32 | 49.95 |  |  |
| 2944.96 | 3.83 | 45.79 |  | 3555.34 | 3.36 | 53.74 |  |  |
| 2973.53 | 3.73 | 46.71 |  | 3583.83 | 3.00 | 50.85 |  |  |
| 3002.19 | 3.72 | 46.75 |  | 3641.38 | 2.98 | 50.16 |  |  |
| 3059.49 | 3.72 | 46.57 |  | 3758.00 | 2.98 | 50.16 | Projected |  |
| 3088.21 | 3.81 | 46.46 |  |  |  |  |  |  |
| 3116.08 | 3.75 | 45.37 |  |  |  |  |  |  |
| 3145.07 | 3.74 | 48.33 |  |  |  |  |  |  |
| 3173.79 | 3.67 | 49.59 |  |  |  |  |  |  |
| 3202.65 | 3.71 | 48.97 |  |  |  |  |  |  |
| 3231.77 | 3.53 | 48.2 |  |  |  |  |  |  |
| 3260.37 | 3.66 | 49.86 |  |  |  |  |  |  |
| 3346.36 | 3.65 | 50.41 |  |  |  |  |  |  |
| 3375.03 | 3.69 | 54.03 |  |  |  |  |  |  |

- WIRELINE SUMMARY:

| Operations Diary | Culverin-1 |
| --- | --- |
| Date | From | To | Total | NPT (w/o) | Remarks |
|  |  |  |  |  | Weak Point Used: 6700-7300 lbs (Blue) |
| 7/Jan/06 | 19:30 | 19:45 | 0:15 |  | JSA on rig floor. Tide 0.5m |
| 7/Jan/06 | 19:45 | 20:35 | 0:50 |  | Pick up sheaves (delay with rig compensator sheave). |
| 7/Jan/06 | 20:35 | 21:15 | 0:40 |  | Pick up tools. |
| 7/Jan/06 | 21:15 | 21:33 | 0:18 |  | Load sources.(Run in hole). |
| 7/Jan/06 | 21:33 | 22:23 | 0:50 |  | RIH to casing shoe. (Compensate on the way at 100m). |
| 7/Jan/06 | 22:23 | 23:30 | 1:07 |  | RIH (Record down-log as precaution but at higher speed-8000ft/hr). |
| 8/Jan/06 | 23:30 | 0:10 | 0:40 |  | Repeat section at 1800ft/hr. (Put on depth.) stretch correction 2.0m |
| 8/Jan/06 | 0:10 | 2:08 | 1:58 |  | Log Main-pass from TD (3757m wireline) 1800ft/hr at high-res (On depth). Stretch correction 2.2m |
| 8/Jan/06 | 2:08 | 3:35 | 1:27 |  | Log up at 3478ft/hr with standard res from 2775m |
| 8/Jan/06 | 3:35 | 4:30 | 0:55 |  | GR to seafloor from 1511m (340mm casing shoe). |
| 8/Jan/06 | 4:30 | 4:55 | 0:25 |  | POOH to surface. |
| 8/Jan/06 | 4:55 | 5:15 | 0:20 |  | Unload sources. |
| 8/Jan/06 | 5:15 | 6:00 | 0:45 |  | Rig down tools. Thermometers 87.8C, 88.9C, 88.9C |

- WELLSITE GEOLOGISTS:

| Mike Woodmansee | Rob Blackmore |
| --- | --- |

- FORMATION TOPS

| WD = 585.0 m RTE = 21.5 m |
| --- |
| FORMATION | PROGNOSED DEPTHS (m) | ACTUAL DEPTHS (m) |
|  | MDKB | TVDSS | THICK | MDKB | TVDSS | HI/LO | THICK | DIFF |
| Sea Floor/ Gippsland Limestone | 607.0 | 585.0 | 1975.0 | 606.5 | 585.0 | 0.0 | 1899.9 | 0.0 |
| Lakes Entrance | 2582.0 | 2560.0 | 325.0 | 2508.0 | 2484.9 | 75.1 H | 315.1 | -10.0 |
| Latrobe | 2907.0 | 2885.0 | 30.0 | 2824.0 | 2800.0 | 85.0 H | 11.0 | -19.0 |
| Base TF Channel | 2937.0 | 2915.0 | 10.0 | 2835.0 | 2811.0 | 104.0 H | 1.0 | -8.0 |
| Top 67.5 Ma Sand | 2947.0 | 2925.0 | 310.0 | 2836.0 | 2812.0 | 113.0 H | 266.5 | -43.5 |
| Near 68.5 Ma Sand | 3257.0 | 3235.0 | 226.0 | 3103.0 | 3078.5 | 156.5 H | 374.3 | -148.3 |
| Near 70.3 Ma Sand | 3482.5 | 3461.0 |  | 3478.0 | 3452.8 | 8.2 H | - | - |
| Near 74 Ma Sand | Not prog | - | - | - | - | - | - | - |
| TD | 3612.0 | 3590.0 | - | 3758.0 | 3732.4 | - | - | - |