## DDR Page 1
DAILY DRILLING REPORT
ESSENTIAL PETROLEUM EXPLORATION Pty Ltd
WELL: |  | EASTWING-1ST |  |  |  |  | DATE: | 2008-09-03 |  | 2008-09-03
PERMIT: |  | PEP 168 |  |  |  |  | REPORT No: | DW0R #3
RIG: |  | Ancon #1 |  |  |  |  | D.F.S. | 0
DEPTH 2400 Hrs: |  | 2293 |  | OPERATIONS at 0600 Hrs: | Pretour Toolbox meeting - Planned operations
| TVD | 0 |  | FORMATION:
| 24 HR PROG.: | N/A | LAST CASING: | 5 1/2: | AT | 2293 | SHOE L.O.T.: | N/A
| HOLE SIZE: | N/A | ELEV: | 59 | RT - GL: | 1.8 | MAASP: | N/A
FROM | TO | HOURS | OPERATIONS
0:00 | 6:00 | 6:00 | Wait on daylight to continue operations.
6:00 | 6:30 | 0:30 | Pretour toolbox meeting - Planned operations - Reviewed EMP with all on site personnel.
6:30 | 8:00 | 1:30 | Continue excavation around cellar and place lower sub base section into position.
8:00 | 12:00 | 4:00 | Pump plastic grease into X bushing cavity to to energise seal - attempt to pressure test -Fluid leaking past
12:00 | 13:00 | 1:00 | Continue to test X bushing - Leaking past 5.50"casing stub (Order additional packing grease from Wood Group.
13:00 | 13:30 | 0:30 | Spot Koomey unit and generator - test Koomey unit to 3000Psi shut down pressure
13:30 | 18:00 | 4:30 | Clean and drift 2.7/8"tubing - rigging up flare line and choke manifold - Install kill line to B section.
18:00 | 24:00 | 6:00 | Wait on daylight to continue operations.
HS&E: No Incidents/ Accidents reported
`
24
OPERATIONS TO 0600 HRS: |  |  | Pre tour Safety Meeting
PROGRAMME NEXT 24 HRS: |  |  | Safety meeting - Repack X bushing - Test X bushing to 3000Psi - Nipple up BOP - Continue Rigging up. |  |  |  |  | rigging up
Prepare tubing and strap same.
WELL COSTS (A$) |  |  | DAILY COST: | 0 |  | CUMULATIVE: | 0
Page 1 of 2

## DDR Page 2
DAILY DRILLING REPORT
ESSENTIAL PETROLEUM EXPLORATION Pty Ltd
WELL: | EASTWING-1ST | [5 empty] | DATE: | 2008-09-03
PERMIT: | PEP 168 | [5 empty] | REPORT No. | DWOR-3
RIG: | Ancon #1 | [5 empty] | D.F.S. | 0
MUD PROPERTIES |  | ADDITIVES |  | SOLIDS | CONTROL |  | SAFETY/BOP/DRILLS
DENSITY(SG) |  |  |  | gpm | uf | hrs | ACCIDENT FREE DAYS |  | 3
VISCOSITY(Secs) |  |  | DESILTER |  |  |  | LAST BOP DRILL |  | N/A
pH |  |  | DESANDER |  |  |  | LAST FIRE DRILL
PV/YP |  |  | CENTRIFUGE 1 |  |  |  | LAST H2S DRILL
GELS 10/10 |  |  | CENTRIFUGE 2 |  |  |  | LAST BOP TEST
WL API (cc/30min) | [6 empty] | BOP TEST DUE
WL HTHP(cc/30min) |  |  | SHAKERS |  |  |  | FORMATION DATA
CAKE(mm) |  |  | SCREENS |  |  |  | DEPTH
SOLIDS % |  |  | PUMPS | 1 | 2 | 3 | TRIP GAS (%)
SAND % |  |  | TYPE |  |  |  | CONN. GAS (%)
CHLORIDES(mg/l) |  |  | STROKE(in) |  |  |  | B'GRD GAS (%)
KCL % |  |  | LINER(in) |  |  |  | PORE PRESS (ppg)
MBT |  |  | SPM |  |  |  | ECD (ppg)
TEMP °C |  |  | GPM |  |  |  | LITHOLOGY
HOLE VOL(bbl) |  |  | SPP ~ psi |  |  |  |  | TIME ANALYSIS
SURF VOL(bbl) |  |  | AV-DP(m/min) |  |  |  |  | HRS | CUM.
LOSSES(bbl/hr) |  |  | AV-DC(m/min) |  |  |  | 1. MOVE RIG
MUD Co |  |  | SCR - spm |  |  |  | 2. RIG UP | 0.5 | 3
MUD TYPE | KCL/PHPA |  | SCR - spm |  |  |  | 3. DRILLING
| BIT DATA |  | BHA DETAILS |  | BHA No. |  | 4. TRIP
BIT No. | N/A |  | TOOL |  | OD (in) | Length (m) | 5. WIPER TRIP
SIZE (in) | [6 empty] | 6. SURVEY
TYPE | [6 empty] | 7. CIRC./COND
IADC CODE | [6 empty] | 8. HANDLE BHA
SERIAL No. | [6 empty] | 9. CASE/CEMENT
NOZZLES(mm) | [6 empty] | 10. WELLHEAD | 5.5 | 5.5
DEPTH IN (m) | [6 empty] | 11. BOPS/DIV
DEPTH OUT (m) | [6 empty] | 12. LOT
DRILLED (m. cum) | [6 empty] | 13. CORING
HOURS (cum.) | [6 empty] | 14. LOGGING |  | 9.5
GRADE | [6 empty] | 15. REAM/WASH
AVGE ROP (m/hr) | [6 empty] | 16. FISH/STUCK
WOB (mt) | [6 empty] | 17. LOSS CIRC
RPM | [6 empty] | 18. KICK CONTROL
JET VEL (m/sec) |  |  | BHA LENGTH (m) |  |  |  | 19. SIDETRACK
HHP @ BIT |  |  | BHA WEIGHT (Klbf) |  |  |  | 20. RIG REPAIR
|  |  | STRING WEIGHT (Klbf) |  |  |  | 21. WELL TEST
SURVEYS: | DEPTH | DEVIATION | AZIMUTH | TVD | COMMENTS |  | 22. WO WEATHER
23. WAIT -WOC
24. ABD./SUSPEND
25. RIG SERVICE
26. SLIP/CUT LINE
[7 empty] | 27. OTHER | 18 | 42.5
COMPLETION
DRILLING TOOLS | SERIAL No. | CUM. HOURS | DRILLING DATA |  |  |  | TOTAL (HRS) | 24 | 60.5
DRAG - UP (Klbf)
DRAG - DOWN (Klbf)
|  |  | TORQUE-On Bottom (Kft.lb) |  | n/a
|  |  | TORQUE-Off Bottom (Kft.lb) |  | n/a
WEATHER | WEATHER STATE |  | RAINFALL (mm) | TEMP.(°C) | VISIBILITY (km) |  | WIND SPEED(kts) | OTHER
| clear |  | Nil | 4-10 | clear |  |  | cool
BULK STOCK | GEL(sx) | BARITE(sx) | CEMENT(sx) | DRILLWATER |  | POT WATER |  | DIESEL FUEL
| 0 | 0 | [5 empty] | 0
PERSONNEL ON RIG |  |  |  | TRANSPORTATION |  | COMMENTS/REQUIREMENTS
OPERATOR |  | 3 | TRUCKS | LOAD | HOURS | Keppel Prince crane - 8.5hrs
DRILLING CONTRACTOR |  | 5
SERVICE COMPANYS
| Mud Logging Crew | 0
| Mud Engineer | 0
| Cementers | 0
| Electric Logging Crew | 5
| DST Crew | 2
OTHERS
| TOTAL | 15
SUPERVISOR | Don Castles |  | ENGINEER | EH | RIG MANAGER |  | Ben Anthony
Page 2 of 2
Note on F25: Dave Hair: 2.4 gps - - .057 Bstk
Note on E23: Dave Hair: .31 b/stk 5.59gals 97%
Note on B40: Dave Hair: 69m first run
Note on B41: Dave Hair: 10.5 hrs first run