| Date: | 17 August 2006 | Licence / State: | P39 (V) / VIC |
| --- | --- | --- | --- |
| Report Period: | 06:00 - 06:00 Hours | Rig: | Ensign 32 |
| Days from Spud: | 19 | GL: | 2.7m |
| Current Hole Size: | 8.5” | RT: | 8.6m |
| Depth @ 0600 Hrs: | 1881m MDRT | PTD: | 2281m MDRT (-1338mSS) |
|  | -957m TVDSS | Spud Date: | 04:30 hrs 29/07/06 |
| 24 Hr Progress: | 0m |  |  |
| Current Operation: | Repairing leaking valve in Top Drive prior to drilling ahead with new Milled Tooth bit |
| Nope Cost (Drill)$ | (C&S)$ |  | Cost To Date: |
|  | (P&A)$ |  |  |

| Casing Data | Hole Size | Depth | Casing Size | Wt: | Type | Shoe Depth | LOT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (Conductor) |  | 100m | 20” |  |  | 60m |  |
|  | 17.5” | 320m | 13.375” | 54.5 | J55 BTC | 317m | EMW= 20.0 ppg |
|  | 12.25” | 1606m | 9.625” | 47.0 | N80 BTC | 1598m * | EMW= 16.7 ppg |

* 9.625m Casing Shoe revised to 1598m based on MWD

| Mud Data | Type: | Wt: | Visc: | WL: | PH: | KCl%: | Cl -: | PV/YP: | Rmf: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | KCL-PHPA | 10.5 | 55 | 5.7 | 9.0 | 6.3 | 38000 | 21 / 26 | 0.11 @ 75(F |

| Bit Data | No. | Make | Type | Size | Hours | Meters | Condition |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (@ 24:00) | 6 | Hycalog | TC | HP21G | 8.5” | - | - | Drill out trip #1 |
|  | 7 | Reed | PDC | RSX272 | 8.5” | 3.0 | 13 | 0-1-RG-G-X-I-NO-BHA |
|  | 8 | Hycalog | PDC | RSX616M | 8.5” | 3.2 | 41 | 2-3-CT-A-X-I-BT-RIG |
|  | 9 | Hycalog | PDC | RSX616M | 8.5” | 3.2 | 20 | 0-0-NO- -X-I-NO-PR |
|  | 9RR | Hycalog | PDC | RSX616M | 8.5” | 14.87 | 201 | 0-0-BU- - X-I-NO-PR |
|  | 10 | Hycalog | Rock | TC11P | 8.5” |  |  |  |

| Surveys | Type | MD (m) | Inclination | Azimuth (T) | TVD (m) | Offset (m) | Direction (T) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | MWD | 1793.14 | 55.54 | 117.44 | 909.28 | 1343.18 | 118.88 |
|  | MWD | 1822.11 | 51.89 | 116.24 | 926.43 | 1366.51 | 118.84 |
|  | MWD | 1851.05 | 47.98 | 115.64 | 945.05 | 1388.63 | 118.80 |

OPERATIONS SUMMARY

Previous 24 hrs Operations Summary: Backream from 1881m to casing shoe. Attempt to unblock jets and balled bit by pumping Baracarb sweep with no apparent improvement in pressure. Pull out of hole to change out balled bit. Download MWD memory data. Pick up Mill Tooth bit, load MWD radioactive sources, shallow test MWD, run in hole to casing shoe. Slip drilling line. Wash and ream to 1833m. Observe leak in mud saver valve in Top Drive. Pull out of hole into casing shoe and repair Top Drive since 04:30 hrs. Anticipated operations: Repair Top Drive. Run back to bottom. Drill ahead 8.5” directional hole, dropping angle to 10( by Top Latrobe.. Sensor Distances: Surveys 9.18m, Gamma Ray 11.65m, Resistivity 14.01m, Pressure 16.54m, Density 22.91m, Porosity 26.97m

| FORMATION TOPS (Preliminary Field picks) |
| --- |
| FORMATION | ACTUAL TOP | High/Low | High/Low | PROGNOSED TOP |
|  | (MDmRT) | (TVDmSS) | To Prognosis | To East Reeve-1 | (MDmRT) | (TVDmSS) |
| Jemmy's Point | 5.9 | 2.7 | - | - | 6 | 3 |
| Tambo River (Coquina) | 143.0 | -134.4 | 30.6m High | 30.8m High | 180 | -165 |
| Gippsland Limestone | 235.0 | -225.9 | 5.9m Low | 0.2m High | 230 | -220 |
| Lakes Entrance Formation |  |  |  |  | 1876 ** | -960 ** |
| Latrobe Coarse Clastics |  |  |  |  | 2098 | -1155 |
| Latrobe N. asperus (Coal) |  |  |  |  | 2163 | -1220 |
| Total Depth |  |  |  |  | 2281 | -1338 |

** Revised Prognosis

HYDROCARBON SHOW SUMMARY

| INTERVAL | LITHOLOGY & HYDROCARBON FLUORESCENCE | GAS |
| --- | --- | --- |

| GAS | MD (m) | Peak | Background | Chromatograph |
| --- | --- | --- | --- | --- |
| Trip Gas | - | - | - | - |
| Connection Gas | - | - | - | - |

| INTERVAL ROP (min/ft) | LITHOLOGY | GAS (Peak / BG) Composition |
| --- | --- | --- |

| 1865-1880m ROP:3.8-11.3 Ave:7.5 | INTERBEDDED CALCAREOUS CLAYSTONE AND MARL CALCAREOUS CLAYSTONE: (60-70%) Medium brown grey, light grey to medium grey, trace off white lithic fragments, trace nod and disseminated pyrite, firm to soft in part, subblocky to subfissile in part. MARL: (30-40%) Pale brown grey, medium grey, argillaceous, rare pyrite, minor dark grey off white lithic fragments, firm to soft in part, subblocky to subfissile in part. | Trace C1 |
| --- | --- | --- |