| Date: | 05 August 2006 | Licence / State: | P39 (V) / VIC |
| --- | --- | --- | --- |
| Report Period: | 06:00 - 06:00 Hours | Rig: | Ensign 32 |
| Days from Spud: | 7 | GL: | 2.7m |
| Current Hole Size: | 12.25” | RT: | 8.6m |
| Depth @ 0600 Hrs: | 1273m MDRT | PTD: | 2281m MDRT (-1338mSS) |
|  | -715m TVDSS | Spud Date: | 04:30 hrs 29/07/06 |
| 24 Hr Progress: | 637m |  |  |
| Current Operation: | Drilling 12.25” Tangent section, holding 71( in the Gippsland Limestone at 30 m/hr. |
| Nope Cost (Drill)$ | (C&S)$ |  | Cost To Date: |
|  | (P&A)$ |  |  |

| Casing Data | Hole Size | Depth | Casing Size | Wt: | Type | Shoe Depth | LOT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (Conductor) |  | 100m | 20” |  |  | 60m |  |
|  | 17.5” | 320m | 13.375” | 54.5 | J55 BTC | 317m | EMW= 20.0 ppg |
|  | 12.25” |  | 9.625” | 47.0 | N80 BTC |  |  |

| Mud Data | Type: | Wt: | Visc: | WL: | PH: | KCl%: | Cl -: | PV/YP: | Rmf: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | KCL | 9.1 | 48 | 6.5 | 9.0 | 5.5 | 28000 | 12 / 21 | - |

| Bit Data | No. | Make | Type | Size | Hours | Meters | Condition |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Reed | Rock | T11C | 17.5” | 0.45 | 20 | 0-0-NO-A-O-I-RR-BHA |
|  | 2RR1 | Reed | Rock | T11C | 17.5” | 2.95 | 200 | 1-1-NO-A-0-I-RR-TD |
|  | 3 | Reed | Rock | T11 | 12.25” | 9.6 | 316 | 0-0-NO-x-0-I-x-BHA |
|  | 4 | Hycalog | PDC | RSX516S | 12.25” | 6.1 | 463 | In hole |

| Surveys | Type | MD (m) | Inclination | Azimuth (T) | TVD (m) | Offset (m) | Direction (T) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | MWD | 1147.01 | 71.72 | 114.43 | 683.87 | 740.32 | 120.71 |
|  | MWD | 1175.95 | 71.38 | 114.73 | 693.03 | 767.62 | 120.49 |
|  | MWD | 1204.93 | 71.66 | 115.31 | 702.22 | 794.99 | 120.30 |
|  | MWD | 1233.87 | 71.80 | 114.62 | 711.29 | 822.35 | 120.13 |

OPERATIONS SUMMARY

Previous 24 hrs Operations Summary: Run in hole with Geopilot assembly to casing shoe. Change out damaged elevators, continue to run in hole and wash last stand to bottom. Drill 12.25” tangent section in the Gippsland Limestone from 636m to 1273m at 06:00 hrs, holding angle at ~71(. Anticipated operations: Drill 12.25” directional hole, holding angle at ~71 degrees to casing point at ~1606m. MWD Sensor to Bit: GR=13m, Survey=9m

| FORMATION TOPS (Preliminary Field picks) |
| --- |
| FORMATION | ACTUAL TOP | High/Low | High/Low | PROGNOSED TOP |
|  | (MDmRT) | (TVDmSS) | To Prognosis | To East Reeve-1 | (MDmRT) | (TVDmSS) |
| Jemmy's Point | 5.9 | 2.7 | - | - | 6 | 3 |
| Tambo River (Coquina) | 143.0 | -134.4 | 30.6m High | 30.8m High | 180 | -165 |
| Gippsland Limestone | 235.0 | -225.9 | 5.9m Low | 0.2m High | 230 | -220 |
| Lakes Entrance Formation |  |  |  |  | 1876 ** | -960 ** |
| Latrobe Coarse Clastics |  |  |  |  | 2098 | -1155 |
| Latrobe N. Asperus (Coal) |  |  |  |  | 2163 | -1220 |
| Total Depth |  |  |  |  | 2281 | -1338 |

** Revised Prognosis

HYDROCARBON SHOW SUMMARY

| INTERVAL | LITHOLOGY & HYDROCARBON FLUORESCENCE | GAS |
| --- | --- | --- |

| GAS | MD (m) | Peak | Background | Chromatograph |
| --- | --- | --- | --- | --- |
| Trip Gas | - | - | - | - |
| Connection Gas | - | - | - | - |

| INTERVAL ROP (min/ft) | LITHOLOGY | GAS (Peak / BG) Composition |
| --- | --- | --- |

| 636-690m ROP:0.7-3.8 Ave:1.5 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (70-90%) Pale grey, light brown, off white, cream, dominantly fine to medium grained, trace echinoid spine & bryozoa fragments, trace shell fragments, trace lithic fragments, trace glauconite, moderately hard to hard, grading to Calcilutite in part. CALCILUTITE: (10-30%) Light brown, light to medium grey, light brown grey, argillaceous, trace dark brown lithic fragments, soft to firm, dispersive. | Nil |
| --- | --- | --- |
| 690-750m ROP:0.8-2.6 Ave: 2.0 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (70-90%) Light grey, light brown grey, off white, fine to medium, trace glauconite, trace fossil fragments, trace dark grey lithic fragments, moderately hard to hard, minor friable, grading to Calcilutite in part. CALCILUTITE: (10-30%) Light grey, off white, argillaceous, trace dark lithic fragments, soft to firm. | Nil |
| 750-830m ROP:0.9-3.2 Ave:1.8 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (50-80%) Light grey, light brown grey, off white, dominantly fine, grading to Calcilutite in part, trace dark lithic fragments, trace glauconite, moderately hard to hard, minor friable. CALCILUTITE: (20-50%) Off white, light grey, argillaceous, trace dark lithic fragments, soft, dispersive. | Nil |
| 830-926m ROP:1.2-2.4 Ave:1.8 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (50-60%) Light grey, off white, light brown grey, dominantly fine, grading to Calcilutite in part, trace dark lithic fragments, rare glauconite grains, trace fossil fragments, moderately hard to hard. CALCILUTITE: (40-50%) Light grey, off white, brown grey, argillaceous, grading to Argillaceous Calcilutite in part, trace dark grey lithic fragments, trace glauconite, soft to firm, dispersive. | Nil |

| INTERVAL ROP (min/ft) | LITHOLOGY | GAS (Peak / BG) Composition |
| --- | --- | --- |

| 926-985m ROP:1.0-2.2 Ave: 1.3 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (40-50%) Light grey, off white, light brown grey, dominantly fine, grading to Calcilutite in part, trace dark lithic fragments, trace rare glauconite grains, trace fossil fragments, moderately hard to hard. CALCILUTITE: (50-60%) Light grey, off white, brown grey, argillaceous, grading to Argillaceous Calcilutite in part, trace dark grey lithic fragments, trace glauconite, soft to firm, dispersive. | Nil |
| --- | --- | --- |
| 985-1120m ROP:0.8-3.2 Ave: 2.2 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (10-40%) Light grey, off white, light brown grey, dominantly fine to occasional very fine grained, grading to Calcilutite in part, trace dark lithic fragments, rare glauconite grains, trace fossil fragments of bryozoa, echinoid spine fragments, occasional forams, moderately hard to hard. CALCILUTITE: (60-90%) Light grey, off white, brown grey, argillaceous, grading to Argillaceous Calcilutite in part, trace dark grey lithic fragments, trace glauconite, soft to firm, dispersive. | Nil |
| 1120-1187m ROP:1.0-3.8 Ave: 2.3 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (30-50%) Light grey, off white, light brown grey, dominantly fine, occasional very fine grained, grading to Calcilutite in part, trace clear calcite cement, trace dark lithic fragments, rare glauconite grains, trace fossil fragments of bryozoa, echinoid spine fragments, rare forams, moderately hard to hard. CALCILUTITE: (50-70%) Light grey, off white, brown grey, argillaceous, grading to Argillaceous Calcilutite in part, trace dark grey lithic fragments, trace glauconite, soft to firm, dispersive. | Nil |
| 1187-1260m ROP:1.6-3.5 Ave:3.0 | INTERBEDDED CALCARENITE AND CALCILUTITE CALCARENITE: (30-50%) Off white, off white, light brown to brown grey, dominantly fine to occasional medium grained, grading to Calcilutite in part, trace opaque calcite cement, trace dark lithic fragments, rare glauconite grains, trace fossil fragments of shells fragments, bryozoa, echinoid spine fragments, rare forams, moderately hard to hard. CALCILUTITE: (50-70%) Light grey, off white, brown grey, argillaceous, grading to Argillaceous Calcilutite in part, trace light brown grey lithic fragments, trace glauconite, dominantly soft to firm, dispersive. | Trace units 12/8/11/29/40 to 37/25/10/28 % |