DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 01, 2006

| RIG 453 | 196 | 363 |
| --- | --- | --- |
| CAMERON | 1671 | 1671 |
| HALLIBURTON | 3458 | 3458 |
| SCHLUMBERGER | 2400 | 2400 |
| ISDL | 196 | 647 |
| ISS | 184 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 01, 2006

Supervisor:	Campbell, Glenn R.

Brigham Bigby

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 30.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $5,113,756 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM & hazard hunts. Install monkey board mast section & monkey board ready for scoping. Dress out monkey board. WOW to scope mast - winds above scoping limits. Complete installing mud pump suction headers, pots & dampers. Continue to run mud pump suction lines. Assist electrician & Mechanic install cables & rig services. Rig Howco compressors into position on workshop roof. Mount possum belly. Install choke & kill lines. Arrange decks, unload equipment & prepare backloading. Run airlift hoses. General rig up operations ongoing. |
| Current: | Installing pump suction lines & airlift hoses. |
| Planned: | Continue general rig up operations. Scope mast when weather conditions permit. |