DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 2, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 259 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 181 | 181 |
| CAMERON | 1734 | 1734 |
| HALLIBURTON | 3538 | 3538 |
| SCHLUMBERGER | 2443 | 2443 |
| ISS | 251 | 2357 |

Well: HLA_A4

Rig/Contractor: 	Rig 453	Report Date: February 2, 2007

Supervisor:	Bigby, Brigham

Campbell, Glenn R

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 9.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $213,739 |  |  |
| Total Cost: | $1,959,448 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: | 641.00/ |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. RIH w/ 9-5/8" surface casing to TD. M/u casing slip assembly & landing jt. Landout casing slips. R/u Howco & cement surface casing. R/d Howco, l/out landing jt & N/d BOP's. Furmanite cut & dress casing stub for B-section. Cameron c/out casing slip seal assembly. WOW - crane shutdown. Continue w/ preparations for drilling production hole while WOW. Weather eased - l/out diverter equipment & diverter riser from wellhead area & BOP bay. |
| Current: | L/out diverter riser. |
| Planned: | N/u B-section & BOP's. |