LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 18 | DFS: | 18 | DATE : | 3-11-09 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1,551 | LAST DEPTH : | 1,478 | 24 HR PROGRESS: | 73 | PTD : |  |
| TOTAL FUEL : | 6,000 | FUEL USAGE : | 1,200 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilling 156mm hole from 1,551m to 1,637m with PDC Bit |
| Next 24 Hrs Op | Drill ahead –wiper trip –survey drill ahead |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 5 Re-Run |  |  | Drilling | 6.5 |  | Density | 1.164 | S.G. |
| Size (mm) | 156 |  |  | Tripping | 8.0 |  | Viscosity | 39 | Sec |
| Make | Smith |  |  | Surveys |  |  | Water Loss |  | Cc |
| Type | MDi613 |  |  | Wireline logging |  |  | pH | 9.5 | Strip |
| IADC Code |  |  |  | Testing/tools | 5.5 |  | Filter Cake | 2 | 32 nd |
| Serial Number | JD1042 |  |  | Circulate Sample |  |  | PV / YP | 10/ 17 | Cp/lb/100’ |
| Nozzles (32) | 3 x 12 |  |  | Casing |  |  | Gels | 3 / 4 | S/m |
| Depth in (m) | 1378 / 1478 |  |  | Cementing |  |  | Sand | 0.40 | % Vol |
| Depth out (m) | 1478 / SIH |  |  | Surveys |  |  | Solids | 7.3 | % Vol |
| Total Metres | 100 / 173 |  |  | Circulate & Condition | 1.0 |  | Oil |  | % Vol |
| Hours | 7.5 / |  |  | Rig Service/slip & cut | 0.5 |  | K+ |  | Mg/l |
| WOB (kg) | 2,000 |  |  | Rig up/ d own bop |  |  | Chlorides | 12,000 | Mg/l |
| RPM | 100 |  |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition |  |  |  | Reaming | 2.5 |  | KCL | 1.8 | % |
| Impact Force | 280 |  |  | Wait On Cement |  |  | Daily Cost $ | 672 |
| Jet Velocity | 232 |  |  | Test BOPs |  |  | Cum Cost $ | 55,824 |
| B.H.A.: 5 | DST Tools Run # 1 |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 1½º N60E | ° at | 1354 | m |  | Type | Amount |
| 0000 | 02.30 | Unseated Packer reversed out gas free slugged pipe |  |  | ° at |  | m |  | AMC Pac L | 2 |
| 02.30 | 03.00 | Rigged down DST surface equipment |  |  | ° at |  | m |  |  |  |
| 03.00 | 06.30 | Tripped out to surface with DST tools |  |  | ° at |  | m |  | Barytes | 32 |
| 06.30 | 08.30 | Layed out tools recovered gauges |  |  | ° at |  | m |  |  |  |
| 08.30 | 10.30 | Tripped in hole to 200m with 156mm drilling assembly |  |  | ° at |  | m |  |  |  |
| 10.30 | 11.00 | Serviced the rig |  |  | ° at |  | m |  |  |  |
| 11.00 | 12.30 | Continued R.I.H to 936m |  |  | ° at |  | m |  |  |  |
| 12.30 | 13.00 | Filled pipe broke circulation |  |  |  |  |
| 13.00 | 14.00 | Continued trip in hole to 1396m |  | PUMP 1 Duplex |  | PUMP 2 Triplex |
| 14.00 | 17.30 | Washed and reamed hole from 1396m to bottom 1478m |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 17.30 | 24.00 | Drilled 156mm hole from 1478m to 1551m |  | Pressure | 8,600 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP | 223 | f/min |  | A.V. DP |  | Ft/min |
|  |  |  |  | A.V. DC | 394 | f/min |  | A.V. DC |  | Ft//mn |
|  |  |  |  | SPM | 40 |  | SPM |  |
|  |  |  |  | GPM | 240 |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 7" | inch |
|  |  | Hunt 17 Camp 4 |  | Class Bulk |  |  | Weight | 26 | ppf |
|  |  | Lakes 3 |  | % |  |  |  | Grade | K-55 |  |
|  |  | Mud logger 2 |  | % |  |  |  | Connection | BTC |  |
|  |  | Farley Riggs 4 |  | % |  |  |  | Joints | 117 |  |
|  |  | RMN 1 |  | % |  |  |  | Length | RT-Brd Hd 5.0 | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 1376m from RKB | m |

,66