LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 3 | DFS: | 3 | DATE : | 19-10-09 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 302m | LAST DEPTH : | 302m | 24 HR PROGRESS: | 0m | PTD : |  |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Tightening up the BOP studs and spools |
| Next 24 Hrs Op | Complete BOP rig up then ,function test same ,pressure test same, make up 216mm drilling assembly |
| Site Personnel: | Hunt Energy 18 Camp 4 Lakes Oil 3 RMN 1 Baker Mud Loggers 2 Halliburton 2 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 Re-run |  |  | Drilling |  |  | Density |  | S.G. |
| Size (mm) | 311 |  |  | Tripping | 3.0 |  | Viscosity |  | Sec |
| Make | Reed |  |  | Slip Cut |  |  | Water Loss |  | Cc |
| Type | EPH41 HKPR |  |  | Rigged up |  |  | pH |  | Strip |
| IADC Code | 4-1-7 |  |  | Testing/tools |  |  | Filter Cake |  | 32 nd |
| Serial Number | NR 2008 |  |  | Circulate Sample |  |  | PV / YP |  | Cp/lb/100’ |
| Nozzles (32) | 18-18-18 |  |  | Casing | 6.5 |  | Gels |  | S/m |
| Depth in (m) | 16 |  |  | Cementing | 1.5 |  | Sand |  | % Vol |
| Depth out (m) | 302 |  |  | Surveys |  |  | Solids |  | % Vol |
| Total Metres | 285 / 846 |  |  | Circulate & Condition | 1.0 |  | Oil |  | % Vol |
| Hours | 18.5 / 63.5 |  |  | Rig Service |  |  | K+ |  | Mg/l |
| WOB (kg) | 2000 |  |  | Rig up/down bop | 6.0 |  | Chlorides |  | Mg/l |
| RPM | 100 |  |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | 2-2-NO-A-E-1-1-CT |  |  | Breakdown kelly |  |  | KCL | % |  |
| Impact Force |  |  |  | Wait On Cement | 6.0 |  | Daily Cost $ | 1,392 |
| Jet Velocity |  |  |  | Test BOPs |  |  | Cum Cost $ | 5,258 |
| B.H.A.: | 311mm bit-NBS-8" DC-STB-8" DC-X/O-8 x 6¼" DC- Drilling Jar-3 x 6¼" DC-4 x HWDP- X/O |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | ¾º | ° at | 32 | m |  | Type | Amount |
| 00.00 | 03.00 | Tripped out ,layed out the 8 " drill collars and 12¼" Stb |  | ½º | ° at | 96 | m |  | Xan-Bore | 30 |
| 03.00 | 06.00 | Rigged up to run 9⅝" Casing |  | 1º | ° at | 239 | m |  |  |  |
| 06.00 | 09.30 | Ran 25jnts Casing plus landing joint shoe at 299m |  | 1½º | ° at | 295 | m |  |  |  |
| 09.30 | 10.00 | Rigged up Halliburton |  |  | ° at |  | m |  |  |  |
| 10.00 | 11.00 | Circulated |  |  | ° at |  | m |  |  |  |
| 11.00 | 11.30 | Held safety meeting ,tested cement lines |  |  | ° at |  | m |  |  |  |
| 11.30 | 12.00 | Cemented Casing ,bumped plug held good |  |  | ° at |  | m |  |  |  |
| 12.00 | 18.00 | W.O.C disconnected flow line, dumped mud pits |  |  |  |  |
| 18.00 | 23.00 | Rigged down Cement head –backed out and layed out |  | PUMP 1 |  | PUMP 2 |
|  |  | the landing joint- cut conductor and layed out same |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 23.00 | 24.00 | Made up the 5K Braden head |  | Pressure |  | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM | 140 |
|  |  |  |  | LPM |  |  | LPM / GPM | 1230 / 325 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 340 | mm |
|  |  | Water from Dyers 1 loads |  | Class Bulk |  |  | Weight | 79.45 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Thread | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 25 |  |
|  |  |  |  | % |  |  |  | Length |  | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 299.00 | m |

,66