## TIME VS DEPTH GRAPH
Trip for bit RSX 616M-A16
Grade: 8-8-RO-A-X-Z-NR-PR
TD @ 2138mRT
Bit: MXL-C30HDX
Grade: 4-6-BT-A-E-I-CT-TD

## DATA
[15 empty] | Days | Depth |  | Days | Depth | Days | Depth
| PLANNED |  |  | Depth |  | Depth
|  | Cumulative | [7 empty] | Days | Depth | Days | Depth | Days | Depth
| hrs | hrs | days | mRT |  | mRT
Operation |  | 0 | 0 | 78 |  | 78 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mob/Rig up 1st half |  | 0 | 0 | 78 |  | 78
Rig Repair (NPT) |  | 0 | 0 | 78 |  | 78
Mob/Rig up 2nd half |  | 152.4 | 6.35 | 78 |  | 78 |  |  |  | 1 | 200 | 1 | 250 | 0.5 | 123
Drill 36in hole - 104m (seabed) - 155m |  | 152.4 | 6.35 | 78 |  | 78
Foundation subsidence precautions |  | 152.4 | 6.35 | 78 |  | 78
Drill 36in hole - 155m - 218m |  | 169.44 | 7.06 | 216 |  | 216 |  |  |  | 2 | 600 | 2 | 500 | 1 | 123
Run and cement 30in conductor |  | 201.12 | 8.38 | 216 |  | 216 |  |  |  | 3 | 850 | 3 | 850 | 2 | 123
Drill 16in hole |  | 252.96 | 10.54 | 810 |  | 810 |  |  |  | 4 | 850 | 4 | 850 | 3 | 123
Run and cement 13.375in casing |  | 303.84 | 12.66 | 810 |  | 810 |  |  |  | 5 | 1000 | 5 | 1200 | 4 | 123
Drill 12.25in hole |  | 432.72 | 18.03 | 2133 |  | 2133 |  |  |  | 6 | 1200 | 6 | 1500 | 5 | 680
Log 12.25in hole |  | 468.24 | 19.51 | 2133 |  | 2133 |  |  |  | 7 | 1600 | 7 | 1600 | 5.5 | 750
Abandon well |  | 566.16 | 23.59 | 2133 |  | 2133 |  |  |  | 8 | 1750 | 8 | 1700 | 6 | 750
Demobilisation |  | 695.76 | 24.99 | 2133 |  | 2133 |  |  |  | 9 | 2100 | 9 | 1700 | 7 | 750
Operation | Day # | Date/Time | Hours |  | Cumulative Days | Cumulative Days | Depth | Cumulative NPT discarded (27.75days) | Comments
Mob/Rig up 1st half | 1 | 2008-10-13 16:00 | 8 | 8 | 0.33333 | 0.33333 | 78 | 0.33333 | On contract: 13-Oct-08 @ 16:00 hrs | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
Mob/Rig up 1st half | 2 | 2008-10-15 | 24 | 32 | 1 | 1.3333 | 78 | 1.3333
Mob/Rig up 1st half | 3 | 2008-10-16 | 24 | 56 | 1 | 2.3333 | 78 | 2.3333
Mob/Rig up 1st half | 4 | 2008-10-16 05:00 | 5 | 61 | 0.20833 | 2.5417 | 78 | 2.5417 | On zero rate: 16-Oct-08 @ 05:00 hrs | [5 empty] | 1 | 200 |  | 1 | 250 | 0.5 | 123
Rig Repair (NPT) | 4 | 2008-10-17 | 19 | 80 | 0.79167 | 3.3333 | 78 | 2.5417
Rig Repair (NPT) | 5 | 2008-10-18 | 24 | 104 | 1 | 4.3333 | 78 | 2.5417
Rig Repair (NPT) | 6 | 2008-10-19 | 24 | 128 | 1 | 5.3333 | 78 | 2.5417 | [6 empty] | 2 | 600 |  | 2 | 500 | 1 | 123
Rig Repair (NPT) | 7 | 2008-10-20 | 24 | 152 | 1 | 6.3333 | 78 | 2.5417 | [6 empty] | 3 | 850 |  | 3 | 850 | 2 | 123
Rig Repair (NPT) | 8 | 2008-10-21 | 24 | 176 | 1 | 7.3333 | 78 | 2.5417 | [6 empty] | 4 | 850 |  | 4 | 850 | 3 | 123
Rig Repair (NPT) | 9 | 2008-10-22 | 24 | 200 | 1 | 8.3333 | 78 | 2.5417 | [6 empty] | 5 | 1000 |  | 5 | 1200 | 4 | 123
Rig Repair (NPT) | 10 | 2008-10-23 | 24 | 224 | 1 | 9.3333 | 78 | 2.5417 | [6 empty] | 6 | 1200 |  | 6 | 1500 | 5 | 680
Rig Repair (NPT) | 11 | 2008-10-24 | 24 | 248 | 1 | 10.3333 | 78 | 2.5417 | [6 empty] | 7 | 1600 |  | 7 | 1600 | 5.5 | 750
Rig Repair (NPT) | 12 | 2008-10-25 | 24 | 272 | 1 | 11.3333 | 78 | 2.5417 | [6 empty] | 8 | 1750 |  | 8 | 1700 | 6 | 750
Rig Repair (NPT) | 13 | 2008-10-26 | 24 | 296 | 1 | 12.3333 | 78 | 2.5417 | [6 empty] | 9 | 2100 |  | 9 | 1700 | 7 | 750
Rig Repair (NPT) | 14 | 2008-10-27 | 24 | 320 | 1 | 13.3333 | 78 | 2.5417 | [6 empty] | 10 | 2200 |  | 10 | 1700 | 8 | 750
Rig Repair (NPT) | 15 | 2008-10-28 | 24 | 344 | 1 | 14.3333 | 78 | 2.5417 | [6 empty] | 11 | 2250 |  | 11 | 1800 | 9 | 1100
Rig Repair (NPT) | 16 | 2008-10-29 | 24 | 368 | 1 | 15.3333 | 78 | 2.5417 | [6 empty] | 12 | 2300 | coring | 12 | 1900 | 10 | 1539
Rig Repair (NPT) | 17 | 2008-10-30 | 24 | 392 | 1 | 16.3333 | 78 | 2.5417 | [6 empty] | 14 |  |  | 14 | 2100 | 12 | 1539
Rig Repair (NPT) | 18 | 2008-10-31 | 24 | 416 | 1 | 17.3333 | 78 | 2.5417 | [6 empty] | 15 |  |  | 15 | 2200 | 13 | 1539
Rig Repair (NPT) | 19 | 2008-11-01 | 24 | 440 | 1 | 18.3333 | 78 | 2.5417 | [6 empty] | 16 |  |  | 16 | 2300 | 14 | 1539
Rig Repair (NPT) | 20 | 2008-11-02 | 24 | 464 | 1 | 19.3333 | 78 | 2.5417 | [6 empty] | 17 |  |  | 17 | 2400 | 15 | 1539
Rig Repair (NPT) | 21 | 2008-11-03 | 24 | 488 | 1 | 20.3333 | 78 | 2.5417
Rig Repair (NPT) | 22 | 2008-11-04 | 24 | 512 | 1 | 21.3333 | 78 | 2.5417 | [6 empty] | 18 |  |  | 18 | 2500 | 16 | 1539
Rig Repair (NPT) | 23 | 2008-11-05 | 24 | 536 | 1 | 22.3333 | 78 | 2.5417 | [6 empty] | 19 |  |  | 19 | 2600 | 17 | 1539
Rig Repair (NPT) | 24 | 2008-11-06 | 24 | 560 | 1 | 23.3333 | 78 | 2.5417 | [6 empty] | 20 |  |  | 20 |  | 18 | 1539
Rig Repair (NPT) | 25 | 2008-11-07 | 24 | 584 | 1 | 24.3333 | 78 | 2.5417 | [6 empty] | 21 |  |  | 21 |  | 19 | 1539
Rig Repair (NPT) | 26 | 2008-11-08 | 24 | 608 | 1 | 25.3333 | 78 | 2.5417 | [11 empty] | 20 | 1539
Rig Repair (NPT) | 27 | 2008-11-09 | 24 | 632 | 1 | 26.3333 | 78 | 2.5417 | [11 empty] | 21 | 1539
Rig Repair (NPT) | 28 | 2008-11-10 | 24 | 656 | 1 | 27.3333 | 78 | 2.5417 | [11 empty] | 22 | 1539
Rig Repair (NPT) | 29 | 2008-11-11 | 24 | 680 | 1 | 28.3333 | 78 | 2.5417 | [11 empty] | 23 | 1539
Rig Repair (NPT) | 30 | 2008-11-12 | 24 | 704 | 1 | 29.3333 | 78 | 2.5417 | [11 empty] | 24 | 1539
Rig Repair (NPT) | 31 | 2008-11-12 23:00 | 23 | 727 | 0.95833 | 30.2917 | 78 | 2.5417 | Off zero rate: 12-Nov-08 @ 23:00 hrs | [10 empty] | 25 | 1539
Mob/Rig up 2nd half | 31 | 2008-11-13 | 1 | 728 | 0.041667 | 30.3333 | 78 | 2.5833 | [11 empty] | 26 | 1539
Mob/Rig up 2nd half | 32 | 2008-11-14 | 24 | 752 | 1 | 31.3333 | 78 | 3.5833
Mob/Rig up 2nd half | 33 | 2008-11-15 | 24 | 776 | 1 | 32.3333 | 78 | 4.5833
Mob/Rig up 2nd half | 34 | 2008-11-15 07:00 | 18.5 | 794.5 | 0.77083 | 33.1042 | 78 | 5.3542
Drill 36in hole - 104m (seabed) - 155m | 34 | 2008-11-15 21:00 | 2.5 | 797 | 0.10417 | 33.2083 | 155 | 5.4583
Foundation subsidence precautions | 34 | 2008-11-16 | 3 | 800 | 0.125 | 33.3333 | 155 | 5.5833
Foundation subsidence precautions | 35 | 2008-11-16 13:30 | 13.5 | 813.5 | 0.5625 | 33.8958 | 155 | 6.1458
Drill 36in hole - 155m - 218m | 35 | 2008-11-16 19:00 | 2.5 | 816 | 0.10417 | 34 | 218 | 6.25
Run and cement 30in conductor | 35 | 2008-11-17 | 8 | 824 | 0.33333 | 34.3333 | 218 | 6.5833
Run and cement 30in conductor | 36 | 2008-11-18 | 24 | 848 | 1 | 35.3333 | 218 | 7.5833
Run and cement 30in conductor | 37 | 2008-11-18 08:00 | 18 | 866 | 0.75 | 36.0833 | 218 | 8.3333
Drill 16in hole - 218m-414m | 37 | 2008-11-19 | 6 | 872 | 0.25 | 36.3333 | 414 | 8.5833
Drill 16in hole - 414m-810m | 38 | 2008-11-19 19:30 | 12.5 | 884.5 | 0.52083 | 36.8542 | 810 | 9.1042
Run and cement 13.375in casing | 38 | 2008-11-20 | 11.5 | 896 | 0.47917 | 37.3333 | 810 | 9.5833
Run and cement 13.375in casing | 39 | 2008-11-20 19:00 | 19 | 915 | 0.79167 | 38.125 | 810 | 10.375
BOPs Risers | 39 | 2008-11-21 | 5 | 920 | 0.20833 | 38.3333 | 810 | 10.5833
BOPs Risers | 40 | 2008-11-21 08:00 | 8 | 928 | 0.33333 | 38.6667 | 810 | 10.9167
Drill 12.25in hole (Pick up BHA) | 40 | 2008-11-22 | 16 | 944 | 0.66667 | 39.3333 | 810 | 11.5833
Drill 12.25in hole (Pick up BHA) | 41 | 2008-11-23 | 9 | 953 | 0.375 | 39.7083 | 810 | 11.2917
Drill 12.25in hole - 810m-1296m | 41 | 2008-11-23 | 15 | 968 | 0.625 | 40.3333 | 1296 | 12.2083
Drill 12.25in hole - 1296m-1454m | 42 | 2008-11-23 14:00 | 14 | 982 | 0.58333 | 40.9167 | 1454 | 12.7917
Bit Trip* - RSX 616M-A16 (8-8-RO-A-X-2-NR-PR) | 42 | 2008-11-24 | 10 | 992 | 0.41667 | 41.3333 | 1454 | 13.2083 | *All cutting structure and blades worn down to bit body
Bit Trip - RSX 616M-A16 (8-8-RO-A-X-2-NR-PR) | 43 | 2008-11-24 08:30 | 8.5 | 1000.5 | 0.35417 | 41.6875 | 1454 | 13.5625
Drill 12.25in hole | 43 | 2008-11-25 | 15.5 | 1016 | 0.64583 | 42.3333 | 1609 | 14.2083
Drill 12.25in hole | 44 | 2008-11-26 | 24 | 1040 | 1 | 43.3333 | 1838 | 15.2083
Drill 12.25in hole | 45 | 2008-11-27 | 24 | 1064 | 1 | 44.3333 | 2058 | 16.2083
Drill 12.25in hole | 46 | 2008-11-27 16:30 | 16.5 | 1080.5 | 0.6875 | 45.0208 | 2183 | 16.8958
Drill 12.25in hole (POOH with BHA)** | 46 | 2008-11-27 12:00 | 7.5 | 1088 | 0.3125 | 45.3333 | 2183 | 17.2083 | ** Bit grade: MXL-C30HDX (4-6-BT-A-E-I-CT-TD)
Drill 12.25in hole (POOH with BHA/lay down excess DP) | 47 | 2008-11-28 07:30 | 7.5 | 1095.5 | 0.3125 | 45.6458 | 2183 | 17.5208
Plug and abandon | 47 | 2008-11-29 | 16.5 | 1112 | 0.6875 | 46.3333 | 2183 | 18.2083
Plug and abandon | 48 | 2008-11-30 | 24 | 1136 | 1 | 47.3333 | 2183 | 19.2083
Plug and abandon | 49 | 2008-12-01 | 24 | 1160 | 1 | 48.3333 | 2183 | 20.2083
Rig down/Demob | 50 | 2008-12-02 | 24 | 1184 | 1 | 49.3333 | 2183 | 21.2083
Rig down/Demob | 51 | 2008-12-03 | 24 | 1208 | 1 | 50.3333 | 2183 | 22.2083
Rig down/Demob | 52 | 2008-12-04 | 24 | 1232 | 1 | 51.3333 | 2183 | 23.2083
Rig down/Demob | 53 | 2008-12-04 15:00 | 15 | 1247 | 0.625 | 51.9583 | 2183 | 23.8333 | Rig 1 nautical mile from location @ 15:00 hrs