Report for : Dan Daniels / Mark Calicutt  / Andy Choy

Compiled by : Mark Smith

| WELL | WKF W5A |
| --- | --- |
| DATE | 12-11-2009 |
| REPORT # | 6 |
| MIDNIGHT ACTIVITY | Back reaming out of hole at 1831.0 mMDRT. |  | ROP DATA (LAST 24 hours) | m/hr | DEPTH (m) |
| MIDNIGHT DEPTH | 3390.0 mMDRT |  | MINIMUM | 12.0 | 3375.0 |
| TVD | 2392.5 mTVDRT |  | MAXIMUM | 102.3 | 3300.0 |
| PROGRESS LAST 24 hrs | 91.0 m |  | AVERAGE | 43.3 | 3299.0 – 3390.0 |

| PRELIMINARY FIELD PICKS | ACTUAL TOP (mMDRT) | ACTUAL TOP (mTVDRT) | ACTUAL TOP (mTVDSS) RT to MSL (41.7m) | HIGH/ LOW (mTVD) | PROGNOSED TOP (mMDRT) | PROGNOSED TOP (mTVDRT) |
| --- | --- | --- | --- | --- | --- | --- |
| Base of High Velocity Channel | 2158.0 | 1643.0 | -1601.3 | 1.3 L | 2153.9 | 1641.7 |
| Top of Lakes Entrance Formation | 2513.0 | 1886.9 | -1845.2 | 8.2 L | 2500.0 | 1878.7 |
| Top of Latrobe Group | 3188.0 | 2289.4 | -2247.7 | 17.7 L | 3147.3 | 2281.7 |
| Top P11 (FSP1) | 3235.0 | 2313.4 | -2271.7 | 13.7 L | 3203.2 | 2299.7 |
| Top Coarse Clastics (SBP3) / M12 | 3268.5 | 2330.4 | -2228.7 | 24.7 L | 3215.2 | 2305.7 |
| Top M13 (PSB7) | 3280.5 | 2336.5 | -2294.8 | 23.8 L | 3229.2 | 2312.7 |
| Top M14 (SB13) | 3322.0 | 2357.6 | -2315.9 | 10.9 L | 3297.2 | 2346.7 |
| Kingfish OOWC | 3318.2 | 2355.7 | -2314.0 | 0 | 3315.3 | 2355.7 |
| Top M15 | 3365.7 | 2380.0 | -2338.3 | 13.3 L | 3337.2 | 2366.7 |
| Total Depth | 3390.00 | 2392.50 | -2350.77 | 6.8 L | 3375.3 | 2385.7 |

| Current Formation | Latrobe Group |
| --- | --- |

| GAS DATA | DEPTH (m) | TOTAL GAS (U) | C1 % | C2 % | C3 % | C4 % | C5 % | H2S ppm |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MAX (Reserval) | 3314.0 | 115.1 | 0.643 | 0.204 | 0.234 | 0.166 | 0.053 | - |
| MAX (GFF) | - | - | - | - | - | - | - | - |
| BG (Reserval) | 3299.0-3390.0 | 15 | 0.046 | 0.014 | 0.023 | 0.028 | 0.024 | - |
| BG (GFF) | - | - | - | - | - | - | - | - |
| TRIP GAS (Reserval) | - | - | - | - | - | - | - | - |
| TRIP GAS (GFF) | - | - | - | - | - | - | - | - |
| CONNECTION GAS | - | - | - | - | - | - | - | - |

| BIT DATA | PRESENT BIT | PREVIOUS BIT |
| --- | --- | --- |
| BIT No. | 1 |  |
| SIZE (in) | 9-7/8 |  |
| MANUFACTURER/TYPE | Reed Hycalog RSR616S |  |
| JETS (/32 inch) | 8 x 16 |  |
| DEPTH IN (m) | 678.5 |  |
| DEPTH OUT (m) | - |  |
| METRES ON RUN (m) | 2711.5 |  |
| HRS ON BTM 24hrs/total | 2.1 / 42.7 |  |
| BIT CONDITION | - |  |
| RPM RANGE 24hrs | 112-120 |  |
| Pump Hrs 24 hrs / total | 16.7 / 97.6 |  |
| Krevs 24 hrs / total | 14.5 / 348.6 |  |

| 24 HOUR SUMMARY | Drill and survey 9-7/8” hole from 3299.0 mMDRT to 3390.0 mMDRT Total Depth. Anadrill downlink to tools to set RSS to neutral position. Circulate and back ream from 3390.0 mMDRT to 3319.0 mMDRT, racking back 1 stand every bottoms up. Continue to back ream at 5 minutes per stand from 3319.0 mMDRT to 2025.0 mMDRT, working string as required due to high torque. At 2025.0 mMDRT drill string stalled at 26 k ft/lb, baseline torque at 6 k ft/lb. Attempt to work string free, unable to rotate or jar up or down. Circulation okay with no pack off. Worked string free at 2025.0 mMDRT. Electrician troubleshoot TDS shut down due to dynamic breaking high temperature alarm. Work string through tight spot and wipe over interval. Continue to back ream from 2025.0 mMDRT to 1831.0 mMDRT. |
| --- | --- |
| 13-11-2009 5 AM UPDATE | Continue to back ream from 1831.0 mMDRT to 1364.0 mMDRT. 3390.0 mMDRT (2392.50 mTVDRT) |