LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 11 | DFS: | 11 | DATE : | 15 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1359m | LAST DEPTH : | 1290m | 24 HR PROGRESS : | 69m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilling 311mm hole at 1382m |
| Next 24 hr OPS: | Drill to 0700hrs. Circ hole clean. Survey. POH for bit change. Continue drilling. |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 3 |  |  | Drilling | 23.0 |  | Density | 1.176 | S.G. |
| Size (mm) | 311 |  |  | Tripping |  |  | Viscosity | 45 | sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 6.0 | cc |
| Type | EBXSC1 |  |  | Reaming/work tight hole |  |  | pH | 9.5 | strip |
| IADC Code | 1.1.7 |  |  | Testing |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10574192 |  |  | Circulate Sample |  |  | PV / YP | 11/21 | cp/lb/100’ |
| Nozzles (32) | 3x16, 1x18 |  |  | Casing |  |  | Gels | 3/5 | s/m |
| Depth in (m) | 1066 |  |  | Cementing |  |  | Sand | 0.5 | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 6.9 | % Vol |
| Total Metres | 293 |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 61.5 |  |  | Rig Service |  |  | K+ | 21,616 | mg/l |
| WOB (kg) | 20,000 |  |  | Test BOP's |  |  | Chlorides | 25,000 | mg/l |
| RPM | 90 |  |  | Repairs | 1.0 |  | PHPA | 1.55 |  |
| Condition | IN |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force | 5.0 |  |  | Wait On Cement |  |  | Daily Cost $ | 3,910 |
| Jet Velocity | 72.6 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 56,669 |
| B.H.A.: | Bit, bit sub, 2x8” DC’s, stabilizer, XO, 18x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 - 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0130 | Drill 311mm hole from 1290m to 1300m |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0130 | 0230 | Rig repair. Hydromatic chain. |  |  | ° at |  | m |  | Sodium Sulphite | 4 |
| 0230 | 2400 | Drill from 1300m to 1359m. |  |  | ° at |  | m |  | Barite | 220 |
|  |  |  |  |  | ° at |  | m |  | Drillzan | 1 |
|  |  |  |  |  | ° at |  | m |  | KCl Tech |  |
|  |  |  |  |  | ° at |  | m |  | PHPA/Biocide | 11/1 |
|  |  |  |  |  | ° at |  | m |  | Caustic Soda | 2 |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 8500 | kPa |  | Pressure | 8500 | kPa |
|  |  |  |  | A.V. DP | 36 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 44 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 50 |  | SPM | 50 |
|  |  |  |  | LPM | 1165 |  | LPM | 1165 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 800 |  | Size | 340 | mm |
|  |  |  |  | Class | A |  | Weight | 81 | kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 26 |  |
|  |  |  |  | % |  |  |  | Length | 303.5 | m |
|  |  |  |  | Av. Wt | 12.5/15.8ppg |  | Shoe | 302.0 | m |

,66