LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 12 | DFS: | 12 | DATE : | 16 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1385m | LAST DEPTH : | 1359m | 24 HR PROGRESS : | 26m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 28,820 | CUM. COST : $ | 736,029 |
| 0600 OPS : | Circulate & condition hole. |
| Next 24 hr OPS: | POH. Run 244mm casing. |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 3 | 2RR |  | Drilling | 7.0 |  | Density | 1.176 | S.G. |
| Size (mm) | 311 | 311 |  | Tripping | 14.0 |  | Viscosity | 48 | sec |
| Make | Security | Security |  | Surveys | 0.5 |  | Water Loss | 5.5 | cc |
| Type | EBXSC1 | XS1 |  | Reaming/work tight hole |  |  | pH | 9.0 | strip |
| IADC Code | 1.1.7 | 1.1.6 |  | Testing |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10574192 | 10406660 |  | Circulate Sample |  |  | PV / YP | 15/28 | cp/lb/100’ |
| Nozzles (32) | 3x16, 1x18 | 1x16, 3x18 |  | Casing |  |  | Gels | 3/6 | s/m |
| Depth in (m) | 1066 | 1385 |  | Cementing |  |  | Sand | 0.5 | % Vol |
| Depth out (m) | 1385 | Wiper trip |  | Wireline |  |  | Solids | 6.1 | % Vol |
| Total Metres | 319 |  |  | Circulate & Condition | 2.5 |  | Oil |  | % Vol |
| Hours | 68.5 |  |  | Rig Service |  |  | K+ | 20,265 | mg/l |
| WOB (kg) | 20,000 |  |  | Test BOP's |  |  | Chlorides | 22,500 | mg/l |
| RPM | 90 |  |  | Repairs |  |  | PHPA | 1.8 |  |
| Condition | 4-3-WT-N-E-2-ER-HR |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force | 5.0 |  |  | Wait On Cement |  |  | Daily Cost $ | 3,976 |
| Jet Velocity | 72.6 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 60,645 |
| B.H.A.: | Bit, bit sub, 2x8” DC’s, stabilizer, XO, 18x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 - 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | Misrun | ° at | 1385 | m |  | Type | Amount |
| 0000 | 0700 | Drill 311mm hole from 1359m to 1385m |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0700 | 0830 | Circulate hole clean. Run carbide – 5% OG. |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 0830 | 0900 | Drop survey. Pump barite slug. |  |  | ° at |  | m |  | Barite | 348 |
| 0900 | 1100 | POH. Work tight hole at 1191m |  |  | ° at |  | m |  | Drillzan | 1 |
| 1100 | 1200 | Circulate hole. Ream tight section. Raise MW to 1.18 |  |  | ° at |  | m |  | KCl Tech |  |
| 1200 | 1830 | POH. Hole condition OK. Minor tight spots. |  |  | ° at |  | m |  | PHPA | 6 |
| 1830 | 1900 | Lay out stabilizer. Recover survey. Pick up bit #2RR |  |  | ° at |  | m |  | Caustic Soda | 1 |
| 1900 | 2400 | RIH. Minor bridges at 665m, 1079m & 1283m |  |  |  |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 8500 | kPa |  | Pressure | 8500 | kPa |
|  |  |  |  | A.V. DP | 36 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 44 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 50 |  | SPM | 50 |
|  |  |  |  | LPM | 1165 |  | LPM | 1165 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 800 |  | Size | 340 | mm |
|  |  |  |  | Class | A |  | Weight | 81 | kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 26 |  |
|  |  |  |  | % |  |  |  | Length | 303.5 | m |
|  |  |  |  | Av. Wt | 12.5/15.8ppg |  | Shoe | 302.0 | m |

,66