LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 14 | DFS: | 14 | DATE : | 18 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1385m | LAST DEPTH : | 1385m | 24 HR PROGRESS : | 0m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 133,817 | CUM. COST : $ | 908,443 |
| 0600 OPS : | Testing BOP’s |
| Next 24 hr OPS: | Drill DV tool. RIH. Drill shoe. Drill 216mm hole. |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 3 |  |  | Drilling |  |  | Density | 1.15 | S.G. |
| Size (mm) | 216 |  |  | Tripping | 2.5 |  | Viscosity | 37 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type | XSC1S |  |  | Reaming/work tight hole |  |  | pH | 8.5 | Strip |
| IADC Code | 1.1.7 |  |  | Testing |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10394939 |  |  | Circulate Sample |  |  | PV / YP | 10/13 | Cp/lb/100’ |
| Nozzles (32) | 3x12 |  |  | Casing | 4.0 |  | Gels | 1/2 | S/m |
| Depth in (m) | 1385 |  |  | Cementing | 4.0 |  | Sand | Tr | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 6.3 | % Vol |
| Total Metres |  |  |  | Circulate & Condition | 4.0 |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service/slip & cut |  |  | K+ | 13,510 | Mg/l |
| WOB (kg) |  |  |  | Test BOP's | 1.5 |  | Chlorides | 15,000 | Mg/l |
| RPM |  |  |  | Repairs |  |  | PHPA | 1.5 |  |
| Condition |  |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 178 |
| Jet Velocity |  |  |  | Nipple Up BOPs | 8.0 |  | Cum Cost $ | 61,415 |
| B.H.A.: | Bit, bit sub, 2x6-1/2” DC’s, stabilizer, XO, 16x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0400 | Continue to run 115 jts 244mm casing to 1366m. |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0400 | 0430 | Install cement head and surface lines. |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 0430 | 0700 | Circulate casing and clean hole. |  |  | ° at |  | m |  | Barite |  |
| 0700 | 0900 | Mix and pump Stage I cement slurry. |  |  | ° at |  | m |  | Drillzan |  |
|  |  | 339sx Class A w/0.24 gps HR-6L at 15.6ppg |  |  | ° at |  | m |  | KCl Tech |  |
|  |  | Release wiper and displace. Bump plug at 0855hrs. |  |  | ° at |  | m |  | PHPA/Biocide | 0/1 |
| 0900 | 0930 | Drop DV dart and open DV tool at 817m. |  |  | ° at |  | m |  | Caustic Soda |  |
| 0930 | 1100 | Circulate casing and clean hole. |  |  |  |  |
| 1100 | 1200 | Mix and pump Stage II cement slurry. |  | PUMP 1 |  | PUMP 2 |
|  |  | 335sx Class A at 15.6ppg. Release wiper and displace. |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  | Bump plug at 1154hrs and close DV tool. |  | Pressure |  | kPa |  | Pressure |  | kPa |
| 1200 | 1400 | Lift BOP’s and install slip assembly with 40,000lbs |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
| 1400 | 2000 | Rig down lines. Cut and dress 244mm casing stub. |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  | Make-up BOP’s. |  | SPM |  |  | SPM |  |
| 2000 | 2130 | Function test BOP’s. Test blind rams/casing and |  | LPM |  |  | LPM |  |
|  |  | Choke manifold to 17,000kPa. |  |  |  |  |
| 2130 | 2300 | Lay down 203mm DC’s and set-up rig floor. |  | CEMENT DATA |  | LAST CASING |
| 2300 | 2400 | Pick up 216mm bit and BHA. |  | Sacks | 800 |  | Size | 244 | mm |
|  |  |  |  | Class | A |  | Weight | 53.6 | kg/m |
|  |  | Reducing mud weight in surface tanks to 1.09 |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 115 |  |
|  |  |  |  | % |  |  |  | Length | 1364 | m |
|  |  |  |  | Av. Wt | 12.5/15.8ppg |  | Shoe | 1366 | m |

,66