LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 25 | DFS: | 25 | DATE : | 13 Jan 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1796m | LAST DEPTH : | 1767m | 24 HR PROGRESS : | 29m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 36,772 | CUM. COST : $ | 1,504,408 |
| 0600 OPS : | Circulating and conditioning mud. Current TD 1812m |
| Next 24 hr OPS: | Drill ahead to core point |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 6 |  |  | Drilling | 7.0 |  | Density | 1.09 | S.G. |
| Size (mm) | 154 |  |  | Tripping | 10.5 |  | Viscosity | 33 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 11.0 | Cc |
| Type | XS4 |  |  | Reaming/work tight hole | 2.0 |  | pH | 11.5 | Strip |
| IADC Code | 2.1.7 |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10408404 |  |  | Circulate Sample |  |  | PV / YP | 6/8 | Cp/lb/100’ |
| Nozzles (32) | 2x10, 1x9 |  |  | Casing |  |  | Gels | ‘1/2 | S/m |
| Depth in (m) | 1767 |  |  | Cementing |  |  | Sand | Tr | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 1.4 | % Vol |
| Total Metres | 29 |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 7 |  |  | Rig Service/slip & cut |  |  | K+ | 64,848 | Mg/l |
| WOB (kg) | 9000 |  |  | Test BOP's | 1.5 |  | Chlorides | 65,600 | Mg/l |
| RPM | 80 |  |  | Repairs |  |  | PHPA | 0.1 |  |
| Condition | IN |  |  | Drill Out | 3.0 |  | ALC - 50 |  |  |
| Impact Force | 10.03 |  |  | Wait On Cement |  |  | Daily Cost $ | 3,030 |
| Jet Velocity | 91 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 99,553 |
| B.H.A.: | Bit, boot basket, bit sub, 2 x 4-3/4” DC’s, stabilizer, 20 x 4-3/4” DC’s, drilling jars, 2 x 4-3/4” DC’s |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0830 | RIH. Strap pipe. Pick up DC’s and additional DP. |  |  | ° at |  | m |  | AMC PAC-R |  |
|  |  | Tag fill (settled barite) bat 1700m |  |  | ° at |  | m |  | Sodium Sulphite | 4 |
| 0830 | 0930 | Lay down XS DP. |  |  | ° at |  | m |  | Barite |  |
| 0930 | 1030 | RIH with last stands DP. |  |  | ° at |  | m |  | Drillzan |  |
| 1030 | 1230 | Displace to new mud and ream fill to 1747m. |  |  | ° at |  | m |  | KCl Tech | 168 |
| 1230 | 1400 | Test BOP’s. |  |  | ° at |  | m |  | PHPA/Soda Ash | 0/4 |
| 1400 | 1700 | Drill out float collar, shoe track and 216mm sump. |  |  | ° at |  | m |  | Caustic Soda | 1 |
| 1700 | 2400 | Drill 154mm hole from 1767m to 1796m |  |  |  |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 9300 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP | 62/94 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 111 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 36 |  | SPM |  |
|  |  |  |  | LPM | 760 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 335 |  | Size | 178 | mm |
|  |  |  |  | Class | A |  | Weight | 38.7 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 48 |  |
|  |  |  |  | % |  |  |  | Length | 561 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1757 | m |

,66