LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 26 | DFS: | 26 | DATE : | 14 Jan 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1832.4m | LAST DEPTH : | 1796m | 24 HR PROGRESS : | 36.4m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 32,020 | CUM. COST : $ | 1,536,428 |
| 0600 OPS : | Core #1 |
| Next 24 hr OPS: | POH. Recover core |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 6 |  |  | Drilling | 10.0 |  | Density | 1.15 | S.G. |
| Size (mm) | 154 |  |  | Tripping | 8.0 |  | Viscosity | 34 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 8.2 | Cc |
| Type | XS4 |  |  | Reaming/work tight hole |  |  | pH | 10.5 | Strip |
| IADC Code | 2.1.7 |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10408404 |  |  | Circulate Sample | 1.5 |  | PV / YP | 7/9 | Cp/lb/100’ |
| Nozzles (32) | 2x10, 1x9 |  |  | Casing |  |  | Gels | ‘1/2 | S/m |
| Depth in (m) | 1767 |  |  | Cementing |  |  | Sand | Tr | % Vol |
| Depth out (m) | 1832.4 |  |  | Wireline |  |  | Solids | 3.0 | % Vol |
| Total Metres | 65.4 |  |  | Circulate & Condition | 3.5 |  | Oil |  | % Vol |
| Hours | 17 |  |  | Rig Service/slip & cut |  |  | K+ | 59,444 | Mg/l |
| WOB (kg) | 9000 |  |  | Test BOP's |  |  | Chlorides | 58,000 | Mg/l |
| RPM | 80 |  |  | Repairs |  |  | PHPA | 0.15 |  |
| Condition | 8-4-WT-A-E-I-NO-CP |  |  | Coring | 1.0 |  | ALC - 50 |  |  |
| Impact Force | 10.03 |  |  | Wait On Cement |  |  | Daily Cost $ | 4,948 |
| Jet Velocity | 91 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 104,501 |
| B.H.A.: | Bit, boot basket, bit sub, 2 x 4-3/4” DC’s, stabilizer, 20 x 4-3/4” DC’s, drilling jars, 2 x 4-3/4” DC’s |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0430 | Drill 154mm hole from 1796m to 1811m |  |  | ° at |  | m |  | AMC PAC-R | 2 |
| 0430 | 0800 | Investigate pressure loss. Raise mud wt due to high |  |  | ° at |  | m |  | Sodium Sulphite | 2 |
|  |  | CG. |  |  | ° at |  | m |  | Barite | 426 |
| 0800 | 1330 | Drill from 1811m to 1832.4m |  |  | ° at |  | m |  | Drillzan | 1 |
| 1330 | 1500 | Circulate sample. |  |  | ° at |  | m |  | KCl Tech | 34 |
| 1500 | 1930 | POH |  |  | ° at |  | m |  | PHPA/Soda Ash | 1/0 |
| 1930 | 2030 | Make up core barrel |  |  | ° at |  | m |  | Caustic Soda |  |
| 2030 | 2400 | RIH |  |  |  |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 9300 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP | 62/94 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 111 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 36 |  | SPM |  |
|  |  |  |  | LPM | 760 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 335 |  | Size | 178 | mm |
|  |  |  |  | Class | A |  | Weight | 38.7 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 48 |  |
|  |  |  |  | % |  |  |  | Length | 561 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1757 | m |

,66