LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 31 | DFS: | 31 | DATE : | 19 Jan 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1990m | LAST DEPTH : | 1971m | 24 HR PROGRESS : | 19m | PTD : | 2000m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 35,369 | CUM. COST : $ | 1,714,517 |
| 0600 OPS : | Lay down drill collars |
| Next 24 hr OPS: | Run 114mm liner. Cement. |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 7 |  |  | Drilling | 6.0 |  | Density | 1.12 | S.G. |
| Size (mm) | 154 |  |  | Tripping | 8.0 |  | Viscosity | 37 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type | XS12S |  |  | Reaming/work tight hole |  |  | pH | 9.5 | Strip |
| IADC Code | 4.3.7 |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10378100 |  |  | Circulate Sample |  |  | PV / YP | 9/14 | Cp/lb/100’ |
| Nozzles (32) | 2x10, 1x9 |  |  | Casing |  |  | Gels | 1/3 | S/m |
| Depth in (m) | 1845 |  |  | Cementing |  |  | Sand | Tr | % Vol |
| Depth out (m) | 1990 |  |  | Wireline | 6.0 |  | Solids | 2.6 | % Vol |
| Total Metres | 145 |  |  | Circulate & Condition | 2.0 |  | Oil |  | % Vol |
| Hours | 26 |  |  | Rig Service/slip & cut | 2.0 |  | K+ | 48,636 | Mg/l |
| WOB (kg) | 10,000 |  |  | Test BOP's |  |  | Chlorides | 52,000 | Mg/l |
| RPM | 80 |  |  | Repairs |  |  | PHPA | 0.35 |  |
| Condition | 2-1-LT-N-F-1-NO-TD |  |  | Coring |  |  | ALC - 50 |  |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 2,432 |
| Jet Velocity |  |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 110,129 |
| B.H.A.: | Bit, bit sub, 2 x 4-3/4” DC’s, stabilizer, 20 x 4-3/4” DC’s, drilling jars, 2 x 4-3/4” DC’s |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0600 | Drill 154mm hole from 1971m to 1990m (TD) |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0600 | 0700 | Circulate and condition hole |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 0700 | 0800 | Wiper trip to 1700m |  |  | ° at |  | m |  | Barite |  |
| 0800 | 0900 | Circulate and condition hole. |  |  | ° at |  | m |  | Drillzan |  |
| 0900 | 1300 | POH |  |  | ° at |  | m |  | KCl Tech |  |
| 1300 | 1900 | Rig up wireline |  |  | ° at |  | m |  | PHPA/Soda Ash |  |
|  |  | Run#1: DLS-MRS-CSS-GR-SP-CAL |  |  | ° at |  | m |  | Caustic Soda |  |
|  |  | Run#2: PDS-CNS-GR-CAL. Rig down |  |  |  |  |
| 1900 | 2100 | Slip and cut drill line |  | PUMP 1 |  | PUMP 2 |
| 2100 | 2400 | RIH with bit |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 8800 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 35 |  | SPM |  |
|  |  |  |  | LPM | 742 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 335 |  | Size | 178 | mm |
|  |  |  |  | Class | A |  | Weight | 38.7 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 48 |  |
|  |  |  |  | % |  |  |  | Length | 561 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1757 | m |

,66