LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 32 | DFS: | 32 | DATE : | 20 Jan 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1990m | LAST DEPTH : | 1990m | 24 HR PROGRESS : | 0m | PTD : | 2000m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 63,625 | CUM. COST : $ | 1,778,142 |
| 0600 OPS : | POH with 114mm liner |
| Next 24 hr OPS: | POH with liner. Wiper trip with bit |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number |  |  |  | Drilling |  |  | Density | 1.12 | S.G. |
| Size (mm) |  |  |  | Tripping | 7.5 |  | Viscosity | 37 | Sec |
| Make |  |  |  | Surveys |  |  | Water Loss | 6.4 | Cc |
| Type |  |  |  | Reaming/work tight hole |  |  | pH | 9.5 | Strip |
| IADC Code |  |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number |  |  |  | Circulate Sample |  |  | PV / YP | 10/13 | Cp/lb/100’ |
| Nozzles (32) |  |  |  | Casing | 15.0 |  | Gels | 1/3 | S/m |
| Depth in (m) |  |  |  | Cementing |  |  | Sand | Tr | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 2.9 | % Vol |
| Total Metres |  |  |  | Circulate & Condition | 1.5 |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service/slip & cut |  |  | K+ | 48,636 | Mg/l |
| WOB (kg) |  |  |  | Test BOP's |  |  | Chlorides | 52,000 | Mg/l |
| RPM |  |  |  | Repairs |  |  | PHPA | 0.35 |  |
| Condition |  |  |  | Coring |  |  | ALC - 50 |  |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 288 |
| Jet Velocity |  |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 110,417 |
| B.H.A.: | Bit, bit sub, 2 x 4-3/4” DC’s, stabilizer, 20 x 4-3/4” DC’s, drilling jars, 2 x 4-3/4” DC’s |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0200 | RIH to TD. 1m fill |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0200 | 0330 | Circulate and condition hole |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 0330 | 0900 | POH. Lay down 16 x 1221mm DC’s |  |  | ° at |  | m |  | Barite | 36 |
| 0900 | 1400 | Prepare 114mm casing and liner hanger |  |  | ° at |  | m |  | Drillzan |  |
| 1400 | 1700 | Run 26 joints 114mm casing. Pick up liner hanger |  |  | ° at |  | m |  | KCl Tech |  |
| 1700 | 2300 | RIH with landing string. Tag TD at 1990m |  |  | ° at |  | m |  | PHPA/Soda Ash |  |
| 2300 | 2400 | Rig up surface lines and circulate liner |  |  | ° at |  | m |  | Caustic Soda |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 3500 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 30 |  | SPM |  |
|  |  |  |  | LPM | 636 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 335 |  | Size | 178 | mm |
|  |  |  |  | Class | A |  | Weight | 38.7 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 48 |  |
|  |  |  |  | % |  |  |  | Length | 561 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1757 | m |

,66