## summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-11-27
PROGRAM
Customer |  | Beach Petroleum |  | Test Type |  | Formation Testing
Customer Representative |  | Phil |  | Test Operator |  | R. McQuatt
Well Name |  | Glenaire #1 |  | Assistant |  | S. Cox
Formation |  | Pretty Hill |  | Crew |  | Penola 1
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Separator |  | 76
F / SI .THP | n/a | n/a | Serial and Type |  | Test Tank |  | n/a
Pcsg | n/a | n/a | Gas Detector |  | On-Site office |  | n/a
Icsg | n/a | n/a | Genset | n/a | Crane truck |  | 198
Scsg | n/a | n/a | Vehicle No. | 189 | Crane truck Kms. |  | 0
|  |  | Vehicle Km's | 70 | Accommodations |  | n/a
SEQUENCE OF EVENTS
24 Hr Summary : |  | 07:15 Depart Penola for location. 08:00 Arrive on location. Hold tool box talk and safety meeting. 09:15 Complete rig up. Pressure test flow line upstream of choke with well gas (400psi). 09:20 Bleed off pressure to sump. 09:22 Bleed off gas head on well to sump. 09:30 Well dead. W/L RIH to tag fluid. 09:35 Begin swabbing. 10:00 Standby until W/L operations are finished and ready for Perforating Operations. 17:00 Depart location. 18:30 Generate Reports.
Forward Plan : |  | Begin Perforating operations.
Time | Description
07:15 | Depart Penola for location. | [6 empty] | 1
08:00 | Arrive on location. Hold tool box talk and safety meeting. | [6 empty] | 1
09:15 | Complete rig up. Pressure test flow line upstream of choke with well gas (400psi). | [6 empty] | 1
09:20 | Bleed off pressure to sump. | [6 empty] | 1
09:22 | Bleed off gas head on well to sump. | [6 empty] | 1
09:30 | Well dead. W/L RIH to tag fluid. | [6 empty] | 1
09:35 | Begin swabbing. | [6 empty] | 1
10:00 | Standby until W/L operations are finished and ready for Perforating Operations. | [6 empty] | 1
17:00 | Depart location. | [6 empty] | 1
18:30 | Generate Reports. | [6 empty] | 1
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
| PRISM control information | Rev 1.0
Date | 2007-11-27
Contractor | SGS Upstream
Rig/crew | Penola 1
Well | Glenaire #1
Type of operation | Formation Testing
24 Hour summary | 07:15 Depart Penola for location. 08:00 Arrive on location. Hold tool box talk and safety meeting. 09:15 Complete rig up. Pressure test flow line upstream of choke with well gas (400psi). 09:20 Bleed off pressure to sump. 09:22 Bleed off gas head on well to sump. 09:30 Well dead. W/L RIH to tag fluid. 09:35 Begin swabbing. 10:00 Standby until W/L operations are finished and ready for Perforating Operations. 17:00 Depart location. 18:30 Generate Reports.
Forward plan | Begin Perforating operations.
Archive file name | glenaire_#1_2007-11-27_formation_testing_penola_1.xls