## summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-11-30
PROGRAM
Customer |  | Beach Petroleum |  | Test Type |  | Formation Testing
Customer Representative |  | Phil |  | Test Operator |  | R. McQuatt
Well Name |  | Glenaire #1 |  | Assistant |  | S. Cox
Formation |  | Pretty Hill |  | Crew |  | Penola 1
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Separator |  | 76
F / SI .THP | n/a | n/a | Serial and Type |  | Test Tank |  | n/a
Pcsg | n/a | n/a | Gas Detector | Drageor | On-Site office |  | n/a
Icsg | n/a | n/a | Genset | n/a | Crane truck |  | 198
Scsg | n/a | n/a | Vehicle No. | 189 | Crane truck Kms. |  | 0
|  |  | Vehicle Km's | 75 | Accommodations |  | n/a
SEQUENCE OF EVENTS
24 Hr Summary : |  | 0900 Depart Penola for location. 1045 Arrive on location. Hold tool box talk and safety meeting. 1115 Rig up tall 80' lubricator for W/L ops. 1217 Rig up perforating guns. 1400 RIH with Guns. 1415 Shoot Perf. Guns. (24psi on wellhead) 1450 Guns at surface. Shut in Master valve. 1525 Open master valve. Begin to run guages. 1535 Install digital pressure recorder on wellhead. 1605 Guages on bottom. Secure wellhead. Clean up tools and depart location. 1730 Generate Reports.
Forward Plan : |  | Perforate 3rd zone. Possible flow.
Time | Description
0900 | Depart Penola for location. | [6 empty] | 1
1045 | Arrive on location. Hold tool box talk and safety meeting. | [6 empty] | 1
1115 | Rig up tall 80' lubricator for W/L ops. | [6 empty] | 1
1217 | Rig up perforating guns. | [6 empty] | 1
1400 | RIH with Guns. | [6 empty] | 1
1415 | Shoot Perf. Guns. (24psi on wellhead) | [6 empty] | 1
1450 | Guns at surface. Shut in Master valve. | [6 empty] | 1
1525 | Open master valve. Begin to run guages. | [6 empty] | 1
1535 | Install digital pressure recorder on wellhead. | [6 empty] | 1
1605 | Guages on bottom. Secure wellhead. Clean up tools and depart location. | [6 empty] | 1
1730 | Generate Reports. | [6 empty] | 1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
CUSTOMER REPRESENTATIVE SIGNATURE

## Test Results
ty Hill |  |  | Customer: |  | Beach Petroleum |  | Well Name: |  | Glenaire 1 |  |  | Formation: |  | Pretty Hills
|  |  | Perforations: |  |  |  | Type Of Test: |  | Formation Testing |  |  | Operator: |  | R. McQuatt
|  |  | Date Of Test: |  | 2007-11-30 | [6 empty] | Control No.:
TIME |  |  | WELLHEAD DATA |  |  |  | SEPARATOR |  | FLOW RATES |  |  | CUMULATIVE PRODUCTION
Date | Time | Elapsed | Tubing | Annulus | Wellhead | Choke | Pressure | Temp | Gas | Oil | Water | Gas | Oil | Water | W.G.R. | O.G.R.
|  | Time | Pressure | Pressure | Temp | Size |  |  | Flow | Flow | Flow
[9 empty] | Rate | Rate | Rate |  |  |  | (BBLS/ | (BBLS/
|  | (Hours) | (PSI) | (PSI) | (ºC) | (64th) | (PSI) | (ºC) | (MMSCFD) | (BPD) | (BPD) | (MMSCF) | (BBLS) | (BBLS) | MMSCF) | MMSCF)
30/11/07 | 2000 | 29.1667 | 24 |  | 34 | 0
30/11/07 | 1415 | 23.4167 | 22 |  | 33 | 0
30/11/07 | 1430 | 23.6667 | 20 |  | 32 | 0
30/11/07 | 1445 | 23.9167 | 20 |  | 32 | 0
33
Test Results

## PRISM
| PRISM control information | Rev 1.0
Date | 2007-11-30
Contractor | SGS Upstream
Rig/crew | Penola 1
Well | Glenaire #1
Type of operation | Formation Testing
24 Hour summary | 0900 Depart Penola for location. 1045 Arrive on location. Hold tool box talk and safety meeting. 1115 Rig up tall 80' lubricator for W/L ops. 1217 Rig up perforating guns. 1400 RIH with Guns. 1415 Shoot Perf. Guns. (24psi on wellhead) 1450 Guns at surface. Shut in Master valve. 1525 Open master valve. Begin to run guages. 1535 Install digital pressure recorder on wellhead. 1605 Guages on bottom. Secure wellhead. Clean up tools and depart location. 1730 Generate Reports.
Forward plan | Perforate 3rd zone. Possible flow.
Archive file name | glenaire_#1_2007-11-30_formation_testing_penola_1.xls