## summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-12-02
PROGRAM
Customer |  | Beach Petroleum |  | Test Type |  | Formation Testing
Customer Representative |  | Phil |  | Test Operator |  | R. McQuatt
Well Name |  | Glenaire #1 |  | Assistant |  | S. Cox
Formation |  | Pretty Hill |  | Crew |  | Penola 1
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Separator |  | 76
F / SI .THP | n/a | n/a | Serial and Type |  | Test Tank |  | n/a
Pcsg | n/a | n/a | Gas Detector | Drageor | On-Site office |  | n/a
Icsg | n/a | n/a | Genset | n/a | Crane truck |  | 198
Scsg | n/a | n/a | Vehicle No. | 189 | Crane truck Kms. |  | 0
|  |  | Vehicle Km's | 70 | Accommodations |  | n/a
SEQUENCE OF EVENTS
24 Hr Summary : |  | 0630 Depart Penola for location. 0700 Arrive on location. Hold tool box talk and safety meeting. 0710 Begin gradient. 0845 Complete Gradient. Remove digital wellhead recorder. 0912 Open well to flow on a 32/64ths on bypass to flare pit. 0915 Shut in at choke. Open well to flow thru bypass to sump. 0920 Begin to Swab well. 1400 Begin to rig out test equipment. 1515 Test equipment rigged out. Begin to rig out W/L equipment. 1715 All equipment rigged out and loaded. Secure well and depart location for town. 1830 Generate Reports.
Forward Plan :
Time | Description
0630 | Depart Penola for location. | [6 empty] | 1
0700 | Arrive on location. Hold tool box talk and safety meeting. | [6 empty] | 1
0710 | Begin gradient. | [6 empty] | 1
0845 | Complete Gradient. Remove digital wellhead recorder. | [6 empty] | 1
0912 | Open well to flow on a 32/64ths on bypass to flare pit. | [6 empty] | 1
0915 | Shut in at choke. Open well to flow thru bypass to sump. | [6 empty] | 1
0920 | Begin to Swab well. | [6 empty] | 1
1400 | Begin to rig out test equipment. | [6 empty] | 1
1515 | Test equipment rigged out. Begin to rig out W/L equipment. | [6 empty] | 1
1715 | All equipment rigged out and loaded. Secure well and depart location for town. | [6 empty] | 1
1830 | Generate Reports. | [6 empty] | 1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
| PRISM control information | Rev 1.0
Date | 2007-12-02
Contractor | SGS Upstream
Rig/crew | Penola 1
Well | Glenaire #1
Type of operation | Formation Testing
24 Hour summary | 0630 Depart Penola for location. 0700 Arrive on location. Hold tool box talk and safety meeting. 0710 Begin gradient. 0845 Complete Gradient. Remove digital wellhead recorder. 0912 Open well to flow on a 32/64ths on bypass to flare pit. 0915 Shut in at choke. Open well to flow thru bypass to sump. 0920 Begin to Swab well. 1400 Begin to rig out test equipment. 1515 Test equipment rigged out. Begin to rig out W/L equipment. 1715 All equipment rigged out and loaded. Secure well and depart location for town. 1830 Generate Reports.
Forward plan | 0
Archive file name | glenaire_#1_2007-12-02_formation_testing_penola_1.xls