DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 01, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 244 | 363 |
| --- | --- | --- |
| CAMERON | 5499 | 5516 |
| HALLIBURTON | 3321 | 3320 |
| SCHLUMBERGER | 2101 | 2100 |
| ISDL | 244 | 647 |
| ISS | 36 | 2342 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 01, 2006

Supervisor:.	Bennett, James M.

Steel, George.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 10.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $199,038 |  |  |
| Total Cost: | $2,196,081 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2480.00/1842.73 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | RIH from 1322m to 1670m. Tight spot. Circulate bottoms up. RIH from 1670m to 2373m. Stuck @ 2373m. Free pipe by working jars. C&C mud. |
| Current: | Wash and ream @ 2480m. |
| Planned: | RIH to btm, C&C mud, POH to change saver sub, RIH to btm, drill to 3438 |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 245 | 363 |
| --- | --- | --- |
| CAMERON | 5500 | 5516 |
| HALLIBURTON | 3322 | 3321 |
| SCHLUMBERGER | 2102 | 2101 |
| ISDL | 245 | 647 |
| ISS | 37 | 2342 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 02, 2006

Supervisor:.	Bennett, James M.

Steel, George.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 11.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $197,170 |  |  |
| Total Cost: | $2,393,251 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2794.00/1942.21 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Cir. bottoms up. Wash/ream to 2794m. Cir. bottoms up. POH from 2794m to 1385m. Back ream from 1385m to 1298m. RIH to 1385m. POH from 1385m to 1272m. Cir. bottoms up. Change s/sub to 4-1/2" IF. Rig service. Trip drills. |
| Current: | Rig service. |
| Planned: | RIH to 2794m. Drill ahead as per program. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 246 | 363 |
| --- | --- | --- |
| CAMERON | 5501 | 5516 |
| HALLIBURTON | 3323 | 3322 |
| SCHLUMBERGER | 2103 | 2102 |
| ISDL | 246 | 647 |
| ISS | 38 | 2342 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 03, 2006

Supervisor:.	Bennett, James M.

Steel, George.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 11.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $197,170 |  |  |
| Total Cost: | $2,393,251 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2794.00/1942.21 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | RIH w/ 4" d/pipe from 1272m to 2479m. Change handling gear to 5" and RIH to 2794m. Drill/steer/survey 8½" hole from 2794m to 3082m. Circulate bottoms up. Drill from3082m to 3140m. Pit drills. |
| Current: | Drill/steer/survey 8½" hole @ 3140m. |
| Planned: | Drill ahead as per program. |