DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 27, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 240 | 363 |
| --- | --- | --- |
| CAMERON | 5495 | 5513 |
| HALLIBURTON | 3317 | 3316 |
| SCHLUMBERGER | 2097 | 2096 |
| ISDL | 240 | 647 |
| ISS | 32 | 2339 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: June 27, 2006

Supervisor:.	Bennett, James M.

Davis, Brian.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 6.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $181,023 |  |  |
| Total Cost: | $1,416,595 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2794.00/1942.36 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Slip/Cut. Rig Service. Change saver sub. Rack back 4" DP. Pick up 5" DP. RIH to 1302m. Tight spot. Respond to Platform Fire Drill. RIH to 1329m. Side tracked well. CBU. POH w/ DP. RIH w/ cement string @ 920m. Held Trip Drills. |
| Current: | RIH w/ 4" cement string to 920m. |
| Planned: | RIH w/ 4" cement string. Pump cement plug. Sidetrack. Drill ahead |