DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 17, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 258 | 363 |
| --- | --- | --- |
| CAMERON | 5510 | 5527 |
| HALLIBURTON | 3332 | 3331 |
| SCHLUMBERGER | 2112 | 2111 |
| ISDL | 258 | 647 |
| ISS | 47 | 2352 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 15, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.3 | AFE Cost/Days: | $7,100,000 |
| Daily Cost: | $758,041 |  |  |
| Total Cost: | $6,041,901 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 3416.70 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Run & land 2-7/8" completion. Pressure test hanger seals to 5000 psi/15 mins. Function test TRSSSV. R/U & test HES slickline. RIH w/ N-test tool to 2700m. Held trip drills. |
| Current: | RIH w/ N-test tool at 2700m. |
| Planned: | Seat test tool. Set packer. Install BPV. N/d BOP's. Install & test tree |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 17, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 259 | 363 |
| --- | --- | --- |
| CAMERON | 5511 | 5527 |
| HALLIBURTON | 3333 | 3332 |
| SCHLUMBERGER | 2113 | 2112 |
| ISDL | 259 | 647 |
| ISS | 48 | 2352 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 16, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.8 | AFE Cost/Days: | $7,100,000 |
| Daily Cost: | $234,703 |  |  |
| Total Cost: | $6,276,604 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 3416.70 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Set production packer. POH w/ N-test tool. Pressure test tubing & PA to 2000 psi. R/d slickline. L/out landing jts & THRT. Set BPV. N/d BOP's. N/u & test xmas tree. Retrieve BPV. Reinstate grating. Release rig to W-27A well. |
| Current: | Rig released from W-31A well to W-27A well. |
| Planned: | Rig released from W-31A well to W-27A well. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 17, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 259 | 363 |
| --- | --- | --- |
| CAMERON | 5511 | 5527 |
| HALLIBURTON | 3333 | 3332 |
| SCHLUMBERGER | 2113 | 2112 |
| ISDL | 259 | 647 |
| ISS | 48 | 2352 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 16, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory

| AFE Number: | L0501G657 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | .5 | AFE Cost/Days: | $5,800,000.00 |
| Daily Cost: | $79,915 |  |  |
| Total Cost: | $79,915 | Planned MD/TVD: | 3093.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 895.00/797.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W27A |
| --- | --- |
| Management Summary: | Prepare for rig skid. R/d hoses, cables, HP lines & accessways. Arrange decks & equipment as required. Pull & service Air Lift string. Install wing valve on. A-section. Reconfigure BOP rams & install BOP test stump. |
| Current: | Preparing to skid rig to W-27A well. |
| Planned: | Skid rig. N/u BOP"s & shell test. M/U BHA & RIH. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 17, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 260 | 363 |
| --- | --- | --- |
| CAMERON | 5512 | 5527 |
| HALLIBURTON | 3334 | 3333 |
| SCHLUMBERGER | 2114 | 2113 |
| ISDL | 260 | 647 |
| ISS | 49 | 2352 |

Well: WKF_W27A

Rig/Contractor: 	Rig 453	Report Date: July 17, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory

| AFE Number: | L0501G657 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 1.5 | AFE Cost/Days: | $5,800,000.00 |
| Daily Cost: | $167,192 |  |  |
| Total Cost: | $247,107 | Planned MD/TVD: | 3093.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 895.00/797.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W27A |
| --- | --- |
| Management Summary: | Prepare for rig skid. R/dn hoses, cables, HP lines & accessways as required. Reinstate Air Lift system. Release & skid rig east to W27A. Secure rig. Reinstate accesways, skid beam storage panels & rig services. Stump test BOP's. |
| Current: | Reinstate stairs, accessways & rig service lines. |
| Planned: | N/dn Abandonment Flange. N/U BOP & shell test. M/U BHA & RIH. |