DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 04, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 243 | 363 |
| --- | --- | --- |
| CAMERON | 5498 | 5516 |
| HALLIBURTON | 3320 | 3319 |
| SCHLUMBERGER | 2100 | 2099 |
| ISDL | 243 | 647 |
| ISS | 35 | 2342 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: July 04, 2006

Supervisor:.	Bennett, James M.

Steel, George A.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 13.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $170,421 |  |  |
| Total Cost: | $2,830.771 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2794.00/1942.36 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Drill/steer/survey 8½" hole from 3140m to 3450m (TD). Circulate hole clean while racking 1 stand every 30 mins. POH with BHA to 2800m. Trip and Pit drill held. |
| Current: | POH with BHA @ 2800m. |
| Planned: | Rig service, RIH to TD, CBU, POH to surface, M/up logging assy, RIH. |