DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 10, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 292 | 363 |
| --- | --- | --- |
| CAMERON | 5478 | 5507 |
| HALLIBURTON | 3301 | 3299 |
| SCHLUMBERGER | 2080 | 2079 |
| ISDL | 292 | 647 |
| ISS | 15 | 2333 |

Well: WKF_W19A

Rig/Contractor: 	Rig 453	Report Date: June 10, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory.

| AFE Number: | L0501G653 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on Loc: | 8.8 | AFE Cost/Days: | $5,200,000.00 |
| Daily Cost: | $210,144 |  |  |
| Total Cost: | $1,731,147 | Planned MD/TVD: | 2682.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2687.00/2373.41 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W19A |
| --- | --- |
| Management Summary: | M/U logging toolstring & RIH w/ logging BHA to TD. P/U to 2630m and deploy logging tools. Log OOH from TD to 2741m. POH to 1690. Log OOH to 1560. POH to 1240. Log OOH to 666m. POH & L/out logging BHA. Held Trip drills. |
| Current: | Clearing Rig Floor of logging equipment. |
| Planned: | M/U cleanout BHA & RIH. Wiper trip to TD. POOH. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 293 | 363 |
| --- | --- | --- |
| CAMERON | 5479 | 5507 |
| HALLIBURTON | 3302 | 3299 |
| SCHLUMBERGER | 2081 | 2080 |
| ISDL | 293 | 647 |
| ISS | 16 | 2333 |

Well: WKF_W19A

Rig/Contractor: 	Rig 453	Report Date: June 11, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory.

| AFE Number: | L0501G653 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on Loc: | 9.8 | AFE Cost/Days: | $5,200,000.00 |
| Daily Cost: | $184,512 |  |  |
| Total Cost: | $1,915,659 | Planned MD/TVD: | 2682.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2687.00/2373.41 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W19A |
| --- | --- |
| Management Summary: | L/out logging toolstring. M/U cleanout BHA & RIH to TD at 2687m. Pump sweep & circulate hole clean. B/ream OOH to 2490m. Pump sweep & circulate hole clean. POOH to 756m. Pump sweep & circulate hole clean. POOH. Held BOP drills. |
| Current: | Racking HWDP & L/out BHA. |
| Planned: | Jet BOP's. C/out UPR's to 4½" x 7" VBR's. Run & cement 7" casing. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 294 | 363 |
| --- | --- | --- |
| CAMERON | 5480 | 5507 |
| HALLIBURTON | 3303 | 3299 |
| SCHLUMBERGER | 2082 | 2081 |
| ISDL | 294 | 647 |
| ISS | 17 | 2333 |

Well: WKF_W19A

Rig/Contractor: 	Rig 453	Report Date: June 12, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory.

| AFE Number: | L0501G653 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on Loc: | 10.7 | AFE Cost/Days: | $5,200,000.00 |
| Daily Cost: | $168,026 |  |  |
| Total Cost: | $2,083,685 | Planned MD/TVD: | 2682.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2687.00/2373.41 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W19A |
| --- | --- |
| Management Summary: | Jet wellhead & BOP's. L/out jetting assembly. C/out UPR's to 4½" x 7" VBR's. M/U 7" shoetrack, test floats & RIH. Cont. RIH w/ 7" casing to 2223.4m. Trip drill |
| Current: | RIH w/ 7" casing at 2223.4m. |
| Planned: | Run 7" casing to 2681m & cement as per program. Set slips. Cut casing. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 295 | 363 |
| --- | --- | --- |
| CAMERON | 5481 | 5507 |
| HALLIBURTON | 3304 | 3299 |
| SCHLUMBERGER | 2083 | 2082 |
| ISDL | 295 | 647 |
| ISS | 18 | 2333 |

Well: WKF_W19A

Rig/Contractor: 	Rig 453	Report Date: June 13, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory.

| AFE Number: | L0501G653 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on Loc: | 11.7 | AFE Cost/Days: | $5,200,000.00 |
| Daily Cost: | $502,884 |  |  |
| Total Cost: | $2,586,569 | Planned MD/TVD: | 2682.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2687.00/2373.41 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W19A |
| --- | --- |
| Management Summary: | RIH to 2681m w/ 7" casing. Circulate & condition mud. Cement 7" casing. WOC. Conduct rig maintenance & prepare for setting slips & casing cut while WOC. L/out & strap tubing. |
| Current: | Continue rig maintenance & strap tubing while WOC |
| Planned: | Set csg slips & cut csg. Install tbg spool . Test casing to 3000psi. |