DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 14, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 296 | 363 |
| --- | --- | --- |
| CAMERON | 5482 | 5508 |
| HALLIBURTON | 3305 | 3300 |
| SCHLUMBERGER | 2084 | 2083 |
| ISDL | 296 | 647 |
| ISS | 19 | 2334 |

Well: WKF_W19A

Rig/Contractor: 	Rig 453	Report Date: June 14, 2006

Supervisor:.	Campbell, Glenn R.

Stead, Cory.

| AFE Number: | L0501G653 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on Loc: | 12.7 | AFE Cost/Days: | $5,200,000.00 |
| Daily Cost: | $224,016 |  |  |
| Total Cost: | $2,810.667 | Planned MD/TVD: | 2682.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2687.00/2373.41 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W19A |
| --- | --- |
| Management Summary: | WOC. N/d BOP's & riser. Install casing slip assembly. Rough cut & dress casing. N/u tubing head spool. Test lower void to 3000 psi/15 mins. N/u BOP's & riser. Test VBR's & Annular to 300/3000 psi. Test 7" casing to 3000 psi/15 mins. |
| Current: | Conduct Rig Service |
| Planned: | R/U & run gauge ring. Run & set MAXR gun assembly. Run2-7/8" completion. |