DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 3, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 288 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 210 | 210 |
| CAMERON | 1763 | 1763 |
| HALLIBURTON | 3567 | 3567 |
| SCHLUMBERGER | 2472 | 2472 |
| ISS | 280 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: March 3, 2007

Supervisor:	Steel, George

Moss, Ross

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 50.75 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $183,108 |  |  |
| Total Cost: | $8,794,603 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Complete P/U & racking 4" XT-39 drill pipe. Service MV Far Scandia. Lost 3 Hrs due to inability to rack 5½" drill pipe -- caused by in sufficient clearance between monkey board & mast fingers. Commence preparations for BOP testing. |
| Current: | General rig up operations |
| Planned: | Continue w/rig up operations. M/U test assembly & test BOP's. P/U & rack 5½" drill pipe. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 3, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 288 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 210 | 210 |
| CAMERON | 1763 | 1763 |
| HALLIBURTON | 3567 | 3567 |
| SCHLUMBERGER | 2472 | 2472 |
| ISS | 280 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: March 3, 2007

Supervisor:	Smith, Gary G

Stead, Cory

| AFE Number: AFE Number: | L0501H210 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 3.13 | AFE Cost/Days: | $6,614,569 |
| Daily Cost: | $186,589 |  |  |
| Total Cost: | $585,119 | Planned MD/TVD: | 2,535.30 / 3,012.05 |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | PTSM's. Construction completed new A-section weld inspections, installed landing base & rigged down equipment. Rig crews continued general rig maintenance & housekeeping during ongoing Construction work phase of operations. Rigged up Howco & grouted conductor annulus. N/u HP riser & BOP's. M/u test assembly. Conducted BCFT & full 14 day BOP stack test. L/out test assembly. |
| Current: | L/out test plug assembly. |
| Planned: | Run wear bushing. P/u drilling assembly. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 4, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 289 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 211 | 211 |
| CAMERON | 1764 | 1764 |
| HALLIBURTON | 3568 | 3568 |
| SCHLUMBERGER | 2473 | 2473 |
| ISS | 281 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: March 4, 2007

Supervisor:	Steel, George

Moss, Ross

Cory Stead

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 51.75 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $184,008 |  |  |
| Total Cost: | $8,978,611 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Continue picking up & racking 4" drill pipe. Lost 10.75 Hrs due to hydraulic repairs. Service TDS & travelling block. Service MV Far Scandia & MV Lady Kari-Ann. |
| Current: | General rig up operations |
| Planned: | Continue w/rig up operations |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 4, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 289 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 211 | 211 |
| CAMERON | 1764 | 1764 |
| HALLIBURTON | 3568 | 3568 |
| SCHLUMBERGER | 2473 | 2473 |
| ISS | 281 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: March 4, 2007

Supervisor:	Smith, Gary G

Campbell, Glenn R

| AFE Number: AFE Number: | L0501H210 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 4.13 | AFE Cost/Days: | $6,614,569 |
| Daily Cost: | $202,733 |  |  |
| Total Cost: | $787,852 | Planned MD/TVD: | 2,535.30 / 3,012.05 |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | PTSM's. Construction completed 20" conductor repairs, set up, orientated & welded on new A-section to 10-3/4" surface casing. Rig crews continued general rig maintenance & housekeeping during ongoing Construction work phase of operations. Worked boats. |
| Current: | Weld out new A-section to surface casing. |
| Planned: | Inspect welds & confirm OK. Install landing base. Grout 10-3/4" X 20" annulus. Pressure test repaired casing. N/u & test BOP's ready to p/u drilling assembly. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 5, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 290 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 212 | 212 |
| CAMERON | 1765 | 1765 |
| HALLIBURTON | 3569 | 3569 |
| SCHLUMBERGER | 2474 | 2474 |
| ISS | 282 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: March 5, 2007

Supervisor:	Steel, George

Moss, Ross

Cory Stead

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 52.75 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $184,008 |  |  |
| Total Cost: | $9,162,619 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Complete P/U & racking 4" XT-39 drill pipe. Service MV Far Scandia. Lost 3 Hrs due to inability to rack 5½" drill pipe -- caused by in sufficient clearance between monkey board & mast fingers. Commence preparations for BOP testing. |
| Current: | General rig up operations |
| Planned: | Continue w/rig up operations. M/U test assembly & test BOP's. P/U & rack 5½" drill pipe. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 5, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 290 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 212 | 212 |
| CAMERON | 1765 | 1765 |
| HALLIBURTON | 3569 | 3569 |
| SCHLUMBERGER | 2474 | 2474 |
| ISS | 282 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: March 5, 2007

Supervisor:	Smith, Gary G

Campbell, Glenn R

| AFE Number: AFE Number: | L0501H210 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 5.13 | AFE Cost/Days: | $6,614,569 |
| Daily Cost: | $193,555 |  |  |
| Total Cost: | $981,4072 | Planned MD/TVD: | 2,535.30 / 3,012.05 |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | PTSM's. Construction completed new A-section weld inspections, installed landing base & rigged down equipment. Rig crews continued general rig maintenance & housekeeping during ongoing Construction work phase of operations. Rigged up Howco & grouted conductor annulus. N/u HP riser & BOP's. M/u test assembly. Conducted BCFT & full 14 day BOP stack test. L/out test assembly. |
| Current: | L/out test plug assembly. |
| Planned: | Run wear bushing. P/u drilling assembly. |