DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 9, 2006

| RIG 453 | 142 | 363 |
| --- | --- | --- |
| CAMERON | 1617 | 1617 |
| HALLIBURTON | 3405 | 3405 |
| SCHLUMBERGER | 2346 | 2346 |
| ISDL | 142 | 647 |
| ISS | 131 | 2347 |

Well: WKF_W23

Rig/Contractor: 	Rig 453	Report Date: October 7, 2006

Supervisor:	Campbell, Glenn R.

Davis, Brian

| AFE Number: | 40000460 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.0 | AFE Cost/Days: | $1,278,800 |
| Daily Cost: | $211,912 |  |  |
| Total Cost: | $766,440 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23 |
| --- | --- |
| Management Summary: | R/down slickline & R/up Schlumberger E-line. P/test lubricator & HLW to 300/1000 psi. M/up and arm 2½" jet cutter. RIH, Correlate and cut tubing @ 2555m. POH & R/dn E-line. Backout tiedowns and release tubing hanger. Circulate well to Platform Effluent system. Pump hi-vis pills to control drink rate. Lay out landing joints and tubing hanger. Lay out 3½" tubing. Held Trip Drill. |
| Current: | Laying out 3½" Production Tubing |
| Planned: | RIH w/ 3½" Tbg x 4" DP string to set cement abandonment plug. |

| RIG 453 | 143 | 363 |
| --- | --- | --- |
| CAMERON | 1618 | 1618 |
| HALLIBURTON | 3406 | 3406 |
| SCHLUMBERGER | 2347 | 2347 |
| ISDL | 143 | 647 |
| ISS | 132 | 2348 |

Well: WKF_W23

Rig/Contractor: 	Rig 453	Report Date: October 8, 2006

Supervisor:	Campbell, Glenn R.

Davis, Brian

| AFE Number: | 40000460 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 5.0 | AFE Cost/Days: | $1,278,800 |
| Daily Cost: | $180,911 |  |  |
| Total Cost: | $947,351 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23 |
| --- | --- |
| Management Summary: | Lay out 3½" Tubing to bottom SPM at 1639m. All tubulars NORM clear. M/up crossover and RIH w/ 4" DP. Tag tubing stub at 2555m. Drink Rate ~17 bph & increasing. Spot 30 bbl hi-vis on bottom. Set 87 sx, 18 bbls 15.8 ppg cement abandonment plug. CIP @ 12:10 hrs. POH to 2483m and reverse circulate. 7 bbls cement returns. WOC. Forward circulate well clean. RIH and tag TOC at 2489m. Pressure test casing/cement to 1000 psi. Displace well to ISW. POH w/ 4" DP. Lay out 3½" Tubing. Service Workboat. Held Trip Drills. WOW. Unable to continue laying out tubing. Crane shutdown due to weather. |
| Current: | Wait on Weather |
| Planned: | RIH and set cement plug #2. |

| RIG 453 | 144 | 363 |
| --- | --- | --- |
| CAMERON | 1619 | 1619 |
| HALLIBURTON | 3407 | 3407 |
| SCHLUMBERGER | 2348 | 2348 |
| ISDL | 144 | 647 |
| ISS | 133 | 2349 |

Well: WKF_W23

Rig/Contractor: 	Rig 453	Report Date: October 9, 2006

Supervisor:	Campbell, Glenn R.

Davis, Brian

| AFE Number: | 40000460 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 6.0 | AFE Cost/Days: | $1,278,800 |
| Daily Cost: | $181,423 |  |  |
| Total Cost: | $1,128,774 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23 |
| --- | --- |
| Management Summary: | Set DGLV & Test tubing to 800 psi. R/dn slickline & Totco BOP. Set BPV in tbg hanger. N/dn Xmas tree. Inspect tbg hanger threads. N/up HP riser & BOP. BCFT. Recover BPV. M/up landing joints & shell test BOP to 300/3000 psi. Attempt to unjay from tbg hanger without success. Review plans with Ops Supt. WOW. Unable to operate crane due to weather. Rig down slickline and clear pipe deck. |
| Current: | Rigging down Slickline |
| Planned: | R/up Schlumberger, Cut & L/out Tubing |