DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 20, 2006

| RIG 453 | 155 | 363 |
| --- | --- | --- |
| CAMERON | 1630 | 1630 |
| HALLIBURTON | 3418 | 3418 |
| SCHLUMBERGER | 2359 | 2359 |
| ISDL | 155 | 647 |
| ISS | 144 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 20, 2006

Supervisor:	George, Steel

Stead, Cory

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 9.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $215,725 |  |  |
| Total Cost: | $1,956,510 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3170.00/2267.69 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Circulate & condition mud. Drill, steer & survey 8½" hole from 2761m to 3170m. Service rig. Held BOP drills. |
| Current: | Drill, steer & survey 8½" hole at 3170m. |
| Planned: | Drill, steer & survey 8½" hole. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 21, 2006

| RIG 453 | 156 | 363 |
| --- | --- | --- |
| CAMERON | 1631 | 1631 |
| HALLIBURTON | 3419 | 3419 |
| SCHLUMBERGER | 2360 | 2360 |
| ISDL | 156 | 647 |
| ISS | 145 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 21, 2006

Supervisor:	George, Steel

Stead, Cory

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 10.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $216,967 |  |  |
| Total Cost: | $2,173,477 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3257.00/2327.16 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Drill, steer & survey 8½" hole from 3170m to 3257m. POOH for bit change to 1628m. Electrical Loom on Top Drive System (TDS) Service Loop became caught in Derrick due to high winds & was disconnected. Unable to M/U TDS. POOH to 915m. Encountered 30 kips overpull. Attempt to pull through w/ no success. Unable to M/U Top Drive to string due to damaged Electrical Loom. Wait on TDS repair. |
| Current: | Waiting for TDS repair. |
| Planned: | Repair TDS. POOH to shoe. Service rig. POOH & L/out BHA. M/U new BHA & RIH. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 22, 2006

| RIG 453 | 157 | 363 |
| --- | --- | --- |
| CAMERON | 1632 | 1632 |
| HALLIBURTON | 3420 | 3420 |
| SCHLUMBERGER | 2361 | 2361 |
| ISDL | 157 | 647 |
| ISS | 146 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 22, 2006

Supervisor:	George, Steel

Stead, Cory

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 11.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $182,475 |  |  |
| Total Cost: | $2,355,952 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3257.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Repair Top Drive System. Pull inside shoe to 612m. Slip & cut drill line. Service rig. POOH to 213m. Rack HWDP & Jars. Break Bit & L/out motor. M/U new BHA & RIH to 2453m. Held Trip Drills. |
| Current: | RIH on 5" DP at 2453m. |
| Planned: | RIH to 3257m. Drill to TD at 3338m. Circulate hole clean. POOH to shoe & circulate hole clean. POOH. R/U & run Reeves logging assembly. |