DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 24, 2006

| RIG 453 | 158 | 363 |
| --- | --- | --- |
| CAMERON | 1633 | 1633 |
| HALLIBURTON | 3421 | 3421 |
| SCHLUMBERGER | 2362 | 2362 |
| ISDL | 158 | 647 |
| ISS | 147 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 24, 2006

Supervisor:	George, Steel

Stead, Cory

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 13.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $184,310 |  |  |
| Total Cost: | $2,758,143 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3338.00/2382.04 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Rack drilling BHA in Derrick. M/U 5" HWDP logging garage & load logging toolstring. RIH to TD at 3338m. Space out & deploy logging tool string. Log OOH to 3030m. POOH to 1414m. Log OOH to 1271m. Held Trip Drills. |
| Current: | Logging OOH at 1271m. |
| Planned: | Complete logging. POOH logging BHA & toolstring. L/out same. M/U cleanout BHA & RIH. Perform wiper trip. |