DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 27, 2006

| RIG 453 | 161 | 363 |
| --- | --- | --- |
| CAMERON | 1636 | 1636 |
| HALLIBURTON | 3424 | 3424 |
| SCHLUMBERGER | 2365 | 2365 |
| ISDL | 161 | 647 |
| ISS | 150 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 27, 2006

Supervisor:	George, Steel

Stead, Cory

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 16.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $523,991 |  |  |
| Total Cost: | $3,682,040 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3338.00/2382.04 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | RIH with 7" casing from 672m to 2971m. Casing held up, circulate clean. RIH & land casing @ 3334m. Circ/condition mud, cement casing. |
| Current: | Cementing 7" casing |
| Planned: | WOC, set csg slips, install tbg spool. |