DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 28, 2006

| RIG 453 | 162 | 363 |
| --- | --- | --- |
| CAMERON | 1637 | 1637 |
| HALLIBURTON | 3425 | 3425 |
| SCHLUMBERGER | 2366 | 2366 |
| ISDL | 162 | 647 |
| ISS | 151 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 28, 2006

Supervisor:	George, Steel

Glenn Campbell

James Bennett

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 17.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $349,015 |  |  |
| Total Cost: | $4,028,930 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3338.00/2382.04 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Complete cementing 7' casing. WOC. N/down BOP/riser & lift same. Set casing slips, rough cut 7" casing. L/out cut 7" casing jnt, remove BOP from well centre & l/out riser. Dress casing stub. |
| Current: | Installing tubing spool & pressure testing same. |
| Planned: | BOP test |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 29, 2006

| RIG 453 | 163 | 363 |
| --- | --- | --- |
| CAMERON | 1638 | 1638 |
| HALLIBURTON | 3426 | 3426 |
| SCHLUMBERGER | 2367 | 2367 |
| ISDL | 163 | 647 |
| ISS | 152 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 29, 2006

Supervisor:	George, Steel

Glenn Campbell

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 18.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $231,825 |  |  |
| Total Cost: | $4,260,755 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3338.00/2382.04 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | N/up & pressure test tubing spool. Complete full BOP pressure test. Pressure test 7" casing 3000psi/15mins. L/out 5" d/pipe from derrick. Work Far Scandia. |
| Current: | L/out 5" d/pipe & working boat. |
| Planned: | Schlum run gauge ring & junk basket. Set MAXR gun. L/out 4" d/pipe. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 30, 2006

| RIG 453 | 164 | 363 |
| --- | --- | --- |
| CAMERON | 1639 | 1639 |
| HALLIBURTON | 3426 | 3426 |
| SCHLUMBERGER | 2368 | 2368 |
| ISDL | 164 | 647 |
| ISS | 153 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 30, 2006

Supervisor:	George, Steel

Glenn Campbell

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 19.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $184,561 |  |  |
| Total Cost: | $4,445,316 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3338.00/2382.04 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Complete l/down 5" d/pipe from derrick. Install wear bushing. R/up Schlumberger & run gauge ring, junk basket & tag TOC @ 3288m. POH. RIH & set MAXR gun to perf 3236.0m-3239.0m & 3241.5m-3244.5m. POH, r/down Schlumberger. L/out 4" d/pipe from derrick. |
| Current: | L/out 4" d/pipe from derrick. |
| Planned: | Run 2-7/8" completion. |