DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 31, 2006

| RIG 453 | 165 | 363 |
| --- | --- | --- |
| CAMERON | 1640 | 1640 |
| HALLIBURTON | 3427 | 3427 |
| SCHLUMBERGER | 2369 | 2369 |
| ISDL | 165 | 647 |
| ISS | 154 | 2357 |

Well: WKF_W23A

Rig/Contractor: 	Rig 453	Report Date: October 31, 2006

Supervisor:	George, Steel

Glenn Campbell

| AFE Number: | L0501G660 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 20.2 | AFE Cost/Days: | $5,948,157 |
| Daily Cost: | $365,142 |  |  |
| Total Cost: | $4,810,458 | Planned MD/TVD: | 3339.00/2797.24 |
| Casing Size: |  | Actual MD/TVD: | 3338.00/2382.04 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23A |
| --- | --- |
| Management Summary: | Complete l/out 4" d/pipe from derrick. Remove catcher plug & jet well head. R/up WFD tong & equipment. RIH w/ 2-7/8" completion as per program to 2643m. Trip drills. |
| Current: | RIH with 2-7/8" completion @ 2643m. |
| Planned: | Land completion, set packer, set BPV & n/down BOP |