DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 26, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 253 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 177 | 177 |
| CAMERON | 1728 | 1728 |
| HALLIBURTON | 3532 | 3532 |
| SCHLUMBERGER | 2437 | 2437 |
| ISS | 245 | 2357 |

Well: HLA_A4

Rig/Contractor: 	Rig 453	Report Date: January 27, 2007

Supervisor:	Stead, Cory

Bigby, Brigham

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 3.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $26,312 |  |  |
| Total Cost: | $523,500 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | Prepare rig for skidding. Skid rig top package to HLA A24 well centre. Install mud pump. N/U diverter & function test. Service MV Far Scandia – offload Schlumberger wireline unit, 9-5/8” casing, directional tools, wellhead equipment & mud chemicals. Wait on weather. |
| Current: | Waiting on weather |
| Planned: | Wait on weather. M/U jetting BHA & RIH to 169m. Wash down & tag top of shoe. Circulate clean. Complete diverter qualifications. Run single shot gyro. Drill & gyro to 250m. POOH & L/out BHA. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 28, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 254 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 178 | 178 |
| CAMERON | 1729 | 1729 |
| HALLIBURTON | 3533 | 3533 |
| SCHLUMBERGER | 2438 | 2438 |
| ISS | 246 | 2357 |

Well: HLA_A4

Rig/Contractor: 	Rig 453	Report Date: January 28, 2007

Supervisor:	Stead, Cory

Bigby, Brigham

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $207,340 |  |  |
| Total Cost: | $732,040 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | Wait on weather. Install wear bushing. RIH to 85m. Function & pressure test diverter. POOH. Conduct rig maintenance while waiting on weather. |
| Current: | Waiting on weather. |
| Planned: | Wait on weather. M/U jetting BHA & RIH to 169m. Wash down & tag top of shoe. Circulate clean. Run single shot gyro. Drill & gyro to 250m. POOH & L/out BHA. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 29, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 255 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 177 | 177 |
| CAMERON | 1730 | 1730 |
| HALLIBURTON | 3534 | 3534 |
| SCHLUMBERGER | 2439 | 2439 |
| ISS | 247 | 2357 |

Well: HLA_A4

Rig/Contractor: 	Rig 453	Report Date: January 29, 2007

Supervisor:	Stead, Cory

Bigby, Brigham

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 5.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $207,340 |  |  |
| Total Cost: | $939,380 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | Wait on weather. Winds in excess of 40 knots. |
| Current: | Wait on weather. |
| Planned: | M/up jetting BHA & RIH to 169m. Wash down & tag top of shoe. Cir clean. Run single shot gyro. Drill and gyro to 250m. POOH and L/out BHA. |