LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 27 | DFS: | 26 | DATE : | 19-04-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1853m | LAST DEPTH : | 1790m | 24 HR PROGRESS: | 63m | PTD : | 2,700 |
| TOTAL FUEL : | 24,000 | FUEL USAGE : | 3,320 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilled 216mm hole from 1853m to 1863m |
| Next 24 Hrs Op | Drill ahead |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 5 | 6 |  | Drilling | 23.50 |  | Density | 1.116 | S.G. |
| Size (mm) | 216 | 216 |  | Tripping |  |  | Viscosity | 38 | Sec |
| Make | Reed | Reed |  | Surveys |  |  | Water Loss | 8.5 | Cc |
| Type | TD43A | TD51A |  | Sip & Cut block line |  |  | pH | 10.5 | Strip |
| IADC Code | 4-3-7 | 5-1-7 |  | Wash and ream |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | W73458 | JK2076 |  | Circulate Sample |  |  | PV / YP | 6 / 8 | Cp/lb/100’ |
| Nozzles (32) | 14-14-14 | 14-14-14 |  | Casing |  |  | Gels | 1 / 2 | S/m |
| Depth in (m) | 1487 | 1790 |  | Cementing |  |  | Sand | tr | % Vol |
| Depth out (m) | 1790 |  |  | BOP |  |  | Solids | 6.8 | % Vol |
| Total Metres | 303 |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 74 |  |  | Rig Service | 0.50 |  | K+ |  | Mg/l |
| WOB (kg) | 10-12.5 |  |  | Make up BHA |  |  | Chlorides | 1,100 | Mg/l |
| RPM | 80 |  |  | Drill out Cmt |  |  | PHPA | 0.10 |  |
| Condition | 2-1-NO-A-E-I-HR |  |  | Repair rig |  |  | KCL |  |  |
| Impact Force | 580 |  |  | Wait On Cement |  |  | Daily Cost $ | 1,707 |
| Jet Velocity | 297 |  |  | F.I.T |  |  | Cum Cost $ | 50,433 |
| B.H.A.: 5 | 216mm Bit-.Bit Sub-NMDC- Stab-1 x 6-1/4” Drill Collar-Stabilizer-10 x 6-1/4” Drill Collars-Jars- 1 x 6-1/4’ Drill Collars- 4 x HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 39.5@108 | ° at | 1628 | m |  | Type | Amount |
| 0000 | 08:30 | Drilled 216mm hole from 1790m to 1810 m |  | 43 @ 110 | ° at | 1722 | m |  | Aus-Gel |  |
| 08:30 | 09:00 | Serviced the rig ( circulated ) |  | 45@ 113 | ° at | 1778 | m |  | Pac L |  |
| 09:00 | 24:00 | Drilled 216mm hole from 1810m to 1853m |  | 15 | ° at | 1268 | m |  | Pac - R | 11 |
|  |  |  |  | 20 | ° at | 1340 | m |  | Barite |  |
|  |  |  |  | 20 plus | ° at | 1440 | m |  | Citric acid |  |
|  |  |  |  | 28.5 | ° at | 1460 | m |  | PHPA/ KCL |  |
|  |  |  |  | 37 | ° at | 1553 | m |  | Caustic Soda |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 108 | mm |  | Liner | 108 | mm |
|  |  |  |  | Pressure | 9,800 | kPa |  | Pressure | 9,800 | KPa |
|  |  |  |  | A.V. DP | 197 | f/min |  | A.V. DP | 197 | f/min |
|  |  |  |  | A.V. DC | 309 | f/min |  | A.V. DC | 309 | f/min |
|  |  |  |  | SPM | 100 |  | SPM | 100 |
|  |  |  |  | GPM | 210 |  | GPM | 210 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton | 900 |  | Size | 244 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 36 | Lb/ft |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | B.T.C |  |
|  |  |  |  | % |  |  |  | Joints | 110 |  |
|  |  |  |  | % |  |  |  | Length | 1291.00 | m |
| Days since | LTA | 327 |  | Av. Wt |  |  | Shoe | 1296m from RKB | m |

,66