LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 15 | DFS: | 14 | DATE : | 7-04-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1262m | LAST DEPTH : | 1298m | 24 HR PROGRESS: | 36m | PTD : | 2,700 |
| TOTAL FUEL : | 18,600 | FUEL USAGE : | 3,500 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Circ-ran survey –pumped pill-tripped out for casing –laying out 8in drill collars at 06:00am |
| Next 24 Hrs Op | Rig up for casing –run casing - cement same |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 2 | 3 |  | Drilling | 14.00 |  | Density | 1.128 | S.G. |
| Size (mm) | 311mm | 311mm |  | Tripping | 5.50 |  | Viscosity | 49 | Sec |
| Make | Reed | Reed |  | Surveys | 1.50 |  | Water Loss | 6.6 | Cc |
| Type | DX8-140A | M4300-PDH |  | Sip & Cut block line | 0.50 |  | pH | 9.0 | Strip |
| IADC Code | S323 | 4-3-7 |  | Wash and ream |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 206579 | BN4133 |  | Circulate Sample |  |  | PV / YP | 14/ 22 | Cp/lb/100’ |
| Nozzles (32) | 7 x 14 | 20-20-20 |  | Casing |  |  | Gels | 4 / 6 | S/m |
| Depth in (m) | 556 | 1070 |  | Cementing |  |  | Sand | tr | % Vol |
| Depth out (m) | 1070 | 1298 |  | Surveys |  |  | Solids | 7.5 | % Vol |
| Total Metres | 514 | 228 |  | Circulate & Condition | 2.00 |  | Oil |  | % Vol |
| Hours | 90.5 |  |  | Rig Service | 0.50 |  | K+ |  | Mg/l |
| WOB (kg) | 12,000 | 12-15000 |  | Pick up BHA |  |  | Chlorides | 1,050 | Mg/l |
| RPM | 80 | 80 |  | Drill out Cmt |  |  | PHPA | 0.20 |  |
| Condition | Not reusable |  |  | Repair rig |  |  | KCL |  |  |
| Impact Force | 656 | 613 |  | Wait On Cement |  |  | Daily Cost $ | 3,595 |
| Jet Velocity | 263 | 234 |  | Test BOPs |  |  | Cum Cost $ | 33,114 |
| B.H.A.: 3 | 311mm Bit-Bit Sub-N.B.S-2 x 8” Drill Collars- Stabilizer-Crossover sub- NMDC- 8 x 6-1/4”DC- Drilling Jars- 2 x 6-1/4DC-4 HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 4-1/4 | ° at | 1040 | m |  | Type | Amount |
| 0000 | 11:00 | Drilled 311mm hole from 1262m to 1288m |  | 15 | ° at | 1276 | m |  | Aus-Gel |  |
| 11:00 | 11:30 | Serviced The Rig |  | 11 deg | ° at | 357 | m |  | Dextrid |  |
| 11:30 | 12:30 | Ran survey on wireline ( mis-run ) |  | 9 deg | ° at | 414 | m |  | Pac - R | 11 |
| 12:30 | 15:30 | Drilled 311mm hole from 1288m to 1298m |  | 3 deg | ° at | 471 | m |  | Barite | 174 |
| 15:30 | 16:30 | Circulated bottoms up |  | 2 deg | ° at | 546 | m |  | Bulk Barite |  |
| 16:30 | 17:00 | Ran survey at 1276m 15deg S 25deg E |  | 2 deg | ° at | 581 | m |  | PHPA/ KCL |  |
| 17:00 | 18:00 | Pumped 2 pills first one not heavy enough |  | 1.5 deg | ° at | 742 | m |  | Caustic Soda |  |
| 18:00 | 20:00 | Wiper tripped to shoe hole good |  |  |  |  |
| 20:00 | 20:30 | Slipped block line |  | PUMP 1 |  | PUMP 2 |
| 20;30 | 24:00 | Tripped back in hole washed down last 2 singles no fill |  | Liner | 108 | mm |  | Liner | 108 | mm |
|  |  |  |  | Pressure | 7,700 | kPa |  | Pressure | 7,700 | KPa |
|  |  |  |  | A.V. DP | 103 | f/min |  | A.V. DP | 103 | f/min |
|  |  |  |  | A.V. DC | 155 | f/min |  | A.V. DC | 155 | f/min |
|  |  |  |  | SPM | 130 |  | SPM | 130 |
|  |  |  |  | GPM | 272 |  | GPM | 272 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 340 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 81 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | B.T.C |  |
|  |  |  |  | % |  |  |  | Joints | 38 |  |
|  |  |  |  | % |  |  |  | Length | 420.00 | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 420 m from RKB | m |

,66