LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 19 | DFS: | 18 | DATE : | 11-04-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1335m | LAST DEPTH : | 1298m | 24 HR PROGRESS: | 37m | PTD : | 2,700 |
| TOTAL FUEL : | 13,400 | FUEL USAGE : | 2,700 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilled 216mm hole from 1335m to 1350m –survey at 1340m 20deg 110deg-circulated hole clean –trip out for BHA change |
| Next 24 Hrs Op | Trip out for BHA change-Trip back in hole – Drill ahead attempting to correct deviation build up to drop downwards |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 4 |  |  | Drilling | 7.00 |  | Density | 1.092 | S.G. |
| Size (mm) | 216 |  |  | Tripping |  |  | Viscosity | 37 | Sec |
| Make | Reed |  |  | Surveys |  |  | Water Loss | 10.00 | Cc |
| Type | DSX-104GH |  |  | Sip & Cut block line |  |  | pH | 11.0 | Strip |
| IADC Code | M 223 |  |  | Wash and ream |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 109683 |  |  | Circulate Sample |  |  | PV / YP | 8 / 12 | Cp/lb/100’ |
| Nozzles (32) | 5 x 14 |  |  | Casing |  |  | Gels | 2 / 3 | S/m |
| Depth in (m) | 1298 |  |  | Cementing |  |  | Sand | tr | % Vol |
| Depth out (m) |  |  |  | Surveys | 2.00 |  | Solids | 5.3 | % Vol |
| Total Metres | 37 |  |  | Circulate & Condition | 1.00 |  | Oil |  | % Vol |
| Hours | 6 |  |  | Rig Service |  |  | K+ |  | Mg/l |
| WOB (kg) | 3,000 |  |  | Make up BHA |  |  | Chlorides | 1,500 | Mg/l |
| RPM | 100 |  |  | Drill out Cmt | 13.00 |  | PHPA | 0.17 |  |
| Condition |  |  |  | Repair rig |  |  | KCL |  |  |
| Impact Force | 352 |  |  | Wait On Cement |  |  | Daily Cost $ | 5,127 |
| Jet Velocity | 1784, |  |  | F.I.T | 1.00 |  | Cum Cost $ | 39,483 |
| B.H.A.: 4 | 216mm PDC Bit-N.B.S-NMDC- 1 x 6-1/4” Drill Collar-Stabilizer-11 x 6-1/4” Drill Collars-Jars- 2 x 6-1/4’ Drill Collars- 4 x HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 5 | ° at | 841 | m |  | Type | Amount |
| 0000 | 00:30 | Ran wire line survey at 841m 5deg 280deg |  | 3 | ° at | 944 | m |  | Aus-Gel |  |
| 00:30 | 03:00 | Continued to drill out cement from 853m to 956m |  | 6.5 | ° at | 1140 | m |  | Pac L | 12 |
| 03:00 | 03:30 | Ran wire line survey at 944m 3deg 230deg |  | 15 | ° at | 1246 | m |  | Pac - R | 5 |
| 03;30 | 08;30 | Continued to drill out cement from 956m to 1116m |  |  | ° at |  | m |  | Barite |  |
| 08;30 | 09:00 | Ran wire line survey at 1140m 6.5deg 3deg N |  |  | ° at |  | m |  | Citric acid | 34 |
| 09:00 | 12;30 | Continued to drill out cement from 1116m to 1256m |  |  | ° at |  | m |  | PHPA/ KCL |  |
| 12:30 | 13:00 | Ran survey on wire line at 1246m 15deg 155deg |  |  | ° at |  | m |  | Caustic Soda |  |
| 13:00 | 15:00 | Drilled out bottom plug-float collar and shoe |  |  |  |  |
| 15:00 | 16:00 | Cleaned hole to bottom at 1298m drilled to 1301m |  | PUMP 1 |  | PUMP 2 |
| 16:00 | 17:00 | Circulated hole clean for F.I.T |  | Liner | 108 | mm |  | Liner | 108 | mm |
| 17;00 | 18:00 | Conducted F.I.T with 9.1ppg mud to EMW of 14.1ppg |  | Pressure | 4,900 | kPa |  | Pressure | 4,900 | KPa |
| 18;00 | 24:00 | Drilled 216mm hole from 1301m to 1335m |  | A.V. DP | 197 | f/min |  | A.V. DP | 197 | f/min |
|  |  |  |  | A.V. DC | 309 | f/min |  | A.V. DC | 309 | f/min |
|  |  |  |  | SPM | 100 |  | SPM | 100 |
|  |  |  |  | GPM | 210 |  | GPM | 210 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton | 900 |  | Size | 244 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 36 | Lb/ft |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | B.T.C |  |
|  |  |  |  | % |  |  |  | Joints | 110 |  |
|  |  |  |  | % |  |  |  | Length | 1291.00 | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 1296m from RKB | m |

,66